## Cluster plan
Activity/ project title | New or existing activity | Brief activity/ project description | Results/ benefits expected by end March 2024 | Strategic alignment: Ministerial priorities | Strategic alignment: SPPC key programme priorities | Activity/ project budget (enter number only) | Funding source(s) | Current status | Comments | What has gone well since April 2022? | What has gone less well since April 2022? | Are there any particular challenges or issues the cluster would flag to the LHB, SPPC or Welsh Government?
Ty Elis – Counselling services | Existing (pre-dates 2022-23 plan) | The counselling service aims to improve access to mental health and wellbeing services. To provide structured therapeutic counselling interventions to relieve persons who are emotionally distressed and to improve coping strategies and resilience in individuals. | Provision of 1,560 hours of counselling sessions. Improvement in patient Warwick Edinburgh Health and Wellbeing scores following completion of counselling. Improved mental health and well-being of patients. Reduction in GP contacts following counselling. | Mental health and emotional well-being | Mental Wellbeing | 50700 | Cluster funding | Started & on track |  | The roll out of Malinko e-sheduler within all GP practices.Enabling the cluster to monitor the efficiency of the service and any identify gaps in daily caseloads, allowing more effect allocation of caseloads across practices. Ongoing SLA with Ty Elis providing counselling services across the cluster. Ongoing SLA with Care and Repair Healthy Homes scheme continues to deliver an alternative, proactive model of care that focuses on early intervention and prevention. | The cluster has been unable to backfill the current HCSW role, despite advertising on 3 separate occasions There continues to be no cluster project that has been mainstream funded by the Health Board to release new funds for new innovation elsewhere. There has been an exponential increase in meetings for the cluster lead to prepare for, attend and action. As a result of reduced staffing of the district nurse service, the cluster chronic condition nurses have had to fill the gaps out of necessity, which has taken them away from a more pro-active approach to housebound healthcare that they were originally assigned to do. | The lack of mainstream funding. The cluster has a number of successful projects that have been in place for a number of years i.e. Counselling service, Healthy Homes service and CRP testing. If these service were main stream funded by the LHB or Welsh Government this would free up cluster funding and would enable the cluster to develop new services and projects.The cluster lead needs more time devoted to the role as the demands put on them have increased significantly ,mainly outside the initial role intended and into other areas of health board and hospital liason.The GP lead for example have all sessions swallowed up with meeting attendance alone without the extra work of email answering/project developement day to day project trouble-shooting and the continued development of the role.
Care and Repair- Healthy Homes Scheme | Existing (pre-dates 2022-23 plan) | This service provides a dedicated Caseworker and Occupational Therapist linked with the GP surgeries in the North Cluster. The service delivers an alternative, proactive model of care that focuses on early intervention and prevention. | 250 patient referrals per annum into scheme. All patients receive: Full Healthy Homes check Falls assessment Trusted assessor’s assessment Occupational therapy assessment Telecare assessment Benefit check Fuel poverty/heating assessment Fire safety check Signposting to relevant support agencies/organisations | Population health | Community Infrastructure | 43598 | Cluster funding | Started & on track
Cluster Pharmacists | Existing (pre-dates 2022-23 plan) | The cluster funds 2 x band 8a pharmacists (1.6 wte) to support and progress the development of pharmaceutical services and the integrated medicine management agenda within the cluster by ensuring safe, evidence based and cost-effective primary care prescribing within the cluster GP practices | Assist cluster practices in the implementation of DOAC registers with the recommendation of DOAC as first-line anticoagulation. Continue to work with cluster practices in the reduction of stroke risk through improved management of atrial fibrillation. Work in collaboration with cluster practices in taking action to reduce the prevalence of risk factors associated with avoidable medicines related harm through the implementation of a multi-faceted intervention and leading to a reduction in medicine prescribing errors. Assisting with medicines related audits and quality assurance nurturing better links with local community pharmacists. | NHS finance and managing within resources | None | 110021 | Cluster funding | Started & on track
Primary Care Nurses | Existing (pre-dates 2022-23 plan) | The cluster funds 2 x band 6 Primary care nurses to provide services for housebound and care home patients ‘bringing the surgery to their homes’ and helping them receive services they might not be receiving otherwise. The Nurses work with the GP and the wider cluster multi-disciplinary team, providing support for patients with chronic conditions. | Increased assessments of chronic condition patients. Support and treatment provided to housebound and care home patients resulting in early identification of conditions that could result in hospital admission. Reduction in acute problems reducing the need for GP emergency home visits. Timely incontinence assessments being provided, which also reduces pressure on carers. Provision of immunisation to housebound patients i.e. COVID, flu and pneumonia. Increased support and care for housebound patients following hospital discharge. | Population health | Community Infrastructure | 89698 | Cluster funding | Started & on track
Health Care Support Workers (HCSW) | Existing (pre-dates 2022-23 plan) | The cluster funds 1 x band 3 HCSW to provide services for housebound and care home patients. The HCSW work closely with the Primary care nurses and within the cluster multi-disciplinary team, providing support for individuals with chronic conditions. | Increased support of chronic condition patients providing support for the primary care nurses. Ensuring housebound patients receive equity of health care. Care home patients will have pre-review checks with the HCSW before full review with the cluster nurses enabling more reviews to be completed. Delivery of support and care for housebound patients following hospital discharge. The HCSW will also support immunisation campaigns. | Population health | Community Infrastructure | 28744 | Cluster funding | Started & on track
Point-Of-Care C-Reactive Protein Testing (CRP) for the diagnosis of Lower Respiratory Tract Infection in GP practices. In addition the cluster is piloting CRP testing at 2 community phamacies within the cluster (due to commence 2023). | Existing (pre-dates 2022-23 plan) | The cluster has an SLA in place with Princess of Wales hospital to provide Quality assurance for the CRP machines based in each practice. The cluster also funds testing kits and controls for practices approximately. | Reduction in inappropriate prescribing of antibiotics and early identification of severe community acquired pneumonia. The use of point of care CRP testing is an efficient and effective way of managing patient care while also reducing inappropriate antibiotic prescribing. | Population health | Community Infrastructure | 13240 | Cluster funding | Started & on track
Malinko eSheduler | Existing (ongoing from 2022-23 plan) | Malinko will enable practices to allocate caseloads in advance to the Primary Care nurses/HCSWs and will allow them to plan their workload. | It will enable the cluster to monitor the efficiency of the service and any identify gaps in daily caseloads, allowing more effect allocation of caseloads across practices. Malikno links with Health Board travel expenses system reducing admin time. Staff check in and out of patients homes via the app and the app has lone worker alarm functionality. The cluster will have read only access to the District Nursing caseload and vice versa which will reduce duplication of work. | Supporting the health and care workforce | Community Infrastructure | 3000 | Cluster funding | Not started
Accelerated Cluster Development | Existing (ongoing from 2022-23 plan) | The cluster is committed to engaging in the ACD model | Clusters and cluster leads to strongly influence local priorities and decision making. Clusters to be able to deliver innovative and agile solutions that meet the needs of their communities. Targeted services to meet particular local needs - with a focus on vulnerable groups to improve health equity. Easier access to primary care services and a wider range of treatment and support options in the community Smart solutions that maintain continuity of care and an holistic, personalised approach An expanded NHS Wales primary care universal offer (no postcode lottery). A real level of coherence between local and regional priorities. Consistency, simplicity and confidence for the public, patients and carers | A Healthier Wales | Accelerated Cluster Development |  | Mixed sources | Not started
Population Segmentation | Existing (ongoing from 2022-23 plan) | Cluster and individual Practices are commited to work with PHW collegues in order to get a better understanding of population health. identifying the areas of need and exploring how these needs can be met in collaratioon with other partners. | The intelligence will enable services and interventions that are already in place to be targeted to individuals according to, not only their current, but future need making their prevention capacity more effective and efficient. More timely, targeted upstream prevention intervention will increase effectiveness and efficiency leading to improved patient outcomes. Where gaps exist, new interventions can be identified from the published evidence with support from Public Health. | Population health | Community Infrastructure |  | Transformation Fund | Started & on track
Strategic Programme for Primary Care | Existing (pre-dates 2022-23 plan) | Development of a workforce strategy across Primary/Community/Social Care to ensure the appropriate mix of skill set and delivery of MDT working across the cluster | A plan across the cluster which is based on population health needs and delivery of sustainable services | Supporting the health and care workforce | Accelerated Cluster Development |  | Mixed sources | Started & on track
Primary Care Model for Wales | Existing (pre-dates 2022-23 plan) | Primary Care Contractors to continue to deliver essential services to their population whilst taking into account COVID restrictions | Access to services to continue in most appropriate way. | A Healthier Wales | Community Infrastructure |  | Mixed sources | Started & on track | Impact of COVID on available workforce cohort/specific skills which could impact on ability to deliver a particular service area.
NHS Wales Operating Framewok - Maintaining Essential Health Services during the COVID 19 Pandemic | Existing (pre-dates 2022-23 plan) | Access to services to continue to improve for patients and re-introduction of any temporary suspended none core and enhanced service provision in line with WG guidance. | To continue to work with Health Board Primary Care Team to ensure plans to work jointly across teams are identified as needed e.g. to provide timely care of frail/elderly at home, to manage long COVID conditions. | Covid-19 response | Community Infrastructure |  | Other specified source | Started & on track | Impact of COVID on available workforce cohort/specific skills which could impact on ability to deliver a particular service area.
Professional training | Existing (pre-dates 2022-23 plan) | The Cluster to provide capacity for training the next generation of practice staff, including GPs and Practice Nurses, CCM Nurse and Cluster Pharmacy Team. | Establish training programmes for medical Students Hub and Spoke Practice Nurse training model and GP Training. | Supporting the health and care workforce | Community Infrastructure |  | Mixed sources | Started & on track | Limited capacity due to covid restrictions.
Bridgend North
HELP: Follow the numbers; click on a cell in the header row for instructions; see 1st row example.
1
Listing activity/ projects: List activities or projects planned to commence during 2023-24, as well as those planned/ initiated in 2022-23 (or earlier, if ongoing).
2
3
Looking back: Brief reflections on delivering the 2022-23 cluster plan.
4
Looking forward: Potential challenges in delivering the 2023-24 cluster plan.