# Greener Primary Care Framework and Award Scheme

January 2022 Quarterly Update

Overview

- Due to be launched Spring 2022, the Greener Primary Care Framework and Award Scheme has been developed to support independent primary care contractors (general practice, community optometry, community pharmacy and primary care dental practice) to improve the environmental sustainability of their day-to-day practice.

- Developed by the Primary Care Hub (within PHW) and in collaboration with a wide range of external stakeholders via the project’s Expert Group, the Framework consists of over 50 actions, of which 29 are generic actions across 7 diverse categories. The full list of actions can be viewed by clicking on the link below:

- Each participating practice will self-select a range of actions to complete per annual review cycle and will submit evidence to the online Framework to demonstrate achievement. Successive levels of award will be given to practices dependent on the number of actions completed.

- Each action is aligned to the NHS Wales Decarbonisation Strategic Delivery Plan, the Wellbeing of Future Generations (Wales) Act 2015, Prudent Healthcare principles and the UN Sustainable Delivery Goals, where possible.

- Practices will be encouraged to work in small local collaboratives or cluster groups to achieve some of the actions.

- The Framework will be online, free of charge and voluntary.

- The Primary Care Hub are working with the charity Students Organising for Sustainability UK (SOS-UK) to develop the online Framework, manage its use and train Welsh University students to become auditors of the evidence submitted by practices.

- The work is also part of the Bevan Exemplar programme this year.

- We are currently entering the pilot phase of the work (January – March 2022). In early December 2021 practices were asked for expressions of interest to work with us to pilot the Framework and test its accessibility, usability and provide general feedback on implementation of a small number of actions.

- 142 practices across Wales and from all 4 settings expressed an interest in participating, of which 12 have been invited to become part of pilot phase 1 and 2. The remaining practices have been invited to participate in the early adopter phase 3 of the pilot.

- Further information on the pilot is included in the FAQ below:

Additional Resources

| Greener Primary Care FAQ | https://primarycareone.nhs.wales/files/greener-primary-care/greener-primary-care-faq-pdf/ |
| --- | --- |
| Plan on a Page | https://primarycareone.nhs.wales/files/greener-primary-care/plan-on-a-page-green-health-pdf/ |
| Digital Leaflet |  |

Further Information

Please contact greenerprimarycare@wales.nhs.uk or visit the Primary Care One website for further information.