## Introduction
Winter Themes 2019/20 Operational Plan Template
Introduction:
· This winter themes 2019/20 operational plan template is intended to aid local planning and delivery of the Winter Themes Outline Framework for the remainder of 2019/20, with the challenges of the winter period in mind.
· It describes seven themes and related actions that have been co-produced with senior NHS clinicians and directors following an in-depth whole system review of winter 18/19. The themes identified provide sufficient flexibility to encourage local innovation and should be considered in addition to any local initiatives already planned or underway.
· The Welsh Government expects each Health Board to use the winter 19/20 outline framework as a guide and describe how it will work with partners to deliver the required action, using this template which is intended to:
o provide Health Boards with a template to baseline their current work streams against each of the themes and set out their improvement plans for winter 2019/20;
o enable Health Boards and local partners to identify what support and assistance they require;
o build a compendium of winter planning good practice across Wales;
o function as a local assurance tool for the Regional Partnership Boards (RPBs); and
o provide consistent data that will enable reliable evaluation of the themes, their perceived effectiveness and future development.
Development of successful local plans will require true local partnership working. Health Boards should lead the development of the operational template and fully engage with all partners within the community and manage the process via their respective RPBs arrangements.
Instructions:
The purpose of this winter 2019/20 operational template is to support local understanding of existing delivery against the seven key themes and Welsh Government expectations. It should act as a useful stocktake for Health Boards and partners, and support co-ordinated implementation of plans, to improve each of the thematic actions throughout the winter period.
For each theme, you are asked to provide the following:
1. Assessment of current position (September 2019) - baseline/current state (e.g. point in time measurement - numerical and contextual)
2. Outline of proposed next steps for winter 2019/20 - future state (e.g. what is it you are going to change? may include multiples steps, specific and measurable)
3. What are your expected benefits and impact? (e.g. based on current state/hypothesis)
4. How are you going to measure? (e.g. what measurements are you going to use to prove it? qualitative and quantitative measures)
5. Partners involved
6. Improvement category (please select from drop down menu of four categories)
7. Areas of good practice (e.g. list areas which could be shared nationally)
8. National support required (e.g. from National Programme teams)
9 Progress on planned actions for each of the winter months
In addition, a Delivery Tool will be developed to enable local teams to measure monthly key performance indicators - this will be developed nationally and shared with Health Boards by the end of September 2019.
Follow up calls will be arranged for key members of Health Board and Trust teams with responsibility for winter delivery to discuss their progress and help shape their submission during the first two weeks of October.
Completed templates should be sent to the Welsh Government (Jamie.wardrop@gov.wales) by 23 October 2019.
1. Connecting up the patient journey;
2. Developing the team around the patient journey;
3. Making the patient and care experience central to every stage of the journey; and
4. Making sure there is capacity to meet patients’ needs at every stage of the journey

## Theme 1
Theme 1: Optimising cross organisational and sector working to support resilience
Progress on Planned Next Steps
No: | Action | Assessment of current position (September 2019) - baseline current state (e.g. Point in time measurement: Numerical and contextual) | Outline of proposed next steps for winter 2019/20 - future state (e.g. what is it you are going to change? May include multiple step, specific & measurable) | What are your expected Benefits and Impact* (e.g. based on current state/hypothesis) | How are you going to measure? (e.g. what measurement are you going to use to prove it? Qualitative and quantitive measures) | Partners involved | Improvement category (please select from drop down menu:) | Areas of good practice (e.g list areas which could be shared nationally) | National support required (e.g. from National Programme teams) | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01
1.1 | There should be local focus on a model for delivery of advance care planning (ACP) to support the management of people in care homes
1.2 | Continue to develop and deploy Stay Well at Home Plans or the My Winter Health Plan which are communicated and supported by primary care practitioners, social care, public service and third sector partners
1.3 | Maximise the direct enhanced services (DES) for care home residents
1.4 | Develop plans for a ‘pharmacists in ED service’, and other parts of the system where they will add value (e.g. clinical hubs/WAST Clinical Support Desk)
1.5 | Make optimal use of the ‘ED well-being and home safe’ service (delivered by British Red Cross) by clearly identifying patients who would benefit from transport and resettlement home
1.6 | Focus on embedding the ‘hospital to a healthier home’ pilots (delivered by care and repair) by enabling case workers to access ward rounds and review medically fit lists

## Theme 2
Theme 2: Urgent primary care / out of hours resilience
Progress on Planned Next Steps
No: | Action | Assessment of current position (September 2019) - baseline current state (e.g. Point in time measurement: Numerical and contextual) | Outline of proposed next steps for winter 2019/20 - future state (e.g. what is it you are going to change? May include multiple step, specific & measurable) | What are your expected Benefits and Impact* (e.g. based on current state/hypothesis) | How are you going to measure? (e.g. what measurement are you going to use to prove it? Qualitative and quantitive measures) | Partners involved | Improvement category (please select relevant category from drop down menu) | Areas of good practice (e.g list areas which could be shared nationally) | National support required (e.g. from National Programme teams) | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01
2.1 | Review of OOH demand and Capacity analysis (111 tool) to produce action plan to align capacity to meet forecasted demand surges
2.2 | Review current OOHs home visits and consider new models e.g. MDT OOHs Home Vists - local scheme to compliment GPs
2.3 | Particular focus on 3 patient pathways: a) Urgent dental access b) Adult mental health crisis response c) Palliative care patients requiring pain relief (within 2 hours)
2.4 | Primary Care GP Escalation Tool (in hours)
2.5 | Collaborate with WAST on the APP Rotational Model
2.6 | Review each cluster OOHs urgent care demand profile
2.7 | Work with each cluster/practices to define and agree appropriate models and infrastructure – target peak demand at weekends and bank holidays. ***More information on accessing the national winter funding budget for UPCPs will be shared with HBs in early September***

## Theme 3
Theme 3: Preventing Unnecessary Conveyance and Admission to Hospital
Progress on Planned Next Steps
No: | Action | Assessment of current position (September 2019) - baseline current state (e.g. Point in time measurement: Numerical and contextual) | Outline of proposed next steps for winter 2019/20 - future state (e.g. what is it you are going to change? May include multiple step, specific & measurable) | What are your expected Benefits and Impact* (e.g. based on current state/hypothesis) | How are you going to measure? (e.g. what measurement are you going to use to prove it? Qualitative and quantitive measures) | Partners involved | Improvement category (please select relevant category from drop down menu) | Areas of good practice (e.g list areas which could be shared nationally) | National support required (e.g. from National Programme teams) | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01
3.1 | The WAST / NCCU review of the non-injured falls response service should be considered by HBs and scaled up if appropriate to reduce unnecessary conveyance
3.2 | Locally HBs should work with WAST to review demand for non injurious falls to implement a complimentary service
3.3 | Work with WAST on missed opportunities to bypass EDs, for example, rapid assessment clinics, direct acute admissions
3.4 | HBs should establish a clear and consistent system for staff to review the WAST stack to avoid unnecessary conveyance of people to hospital settings
3.5 | Work alongside WAST to understand the availability of paramedic capacity to respond to primary care OOH home visits for example through the APP Rotational Model
3.6 | Redirection of patients from Emergency Department to alternative pathways, self-care or relevant community services
3.7 | Work with GPs to ensure their telephone messages provide the appropriate options for optimum outcome for the patient and system
3.8 | Work with WAST on developing pathways that reflect high demand categories and ensure the access criteria and opening times are clear and understand by WAST
3.9 | Improve/increase MDT supported turnaround at the hospital 'front door', for further assessment and support in the individual's own environment (D2RA Pathway 1)

## Theme 4
Theme 4: Discharge to Assess/Recover (D2AR)
Progress on Planned Next Steps
No: | Action | Assessment of current position (September 2019) - baseline current state (e.g. Point in time measurement: Numerical and contextual) | Outline of proposed next steps for winter 2019/20 - future state (e.g. what is it you are going to change? May include multiple step, specific & measurable) | What are your expected Benefits and Impact* (e.g. based on current state/hypothesis) | How are you going to measure? (e.g. what measurement are you going to use to prove it? Qualitative and quantitive measures) | Partners involved | Improvement category (please select relevant category from drop down menu) | Areas of good practice (e.g list areas which could be shared nationally) | National support required (e.g. from National Programme teams) | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01
4.1 | Each HB should align commissioning to the 'Every Day Counts' project and seek to implement D2AR pathways in readiness for Winter 2019/20
4.2 | Each HB will be required to baseline its current activity in relation to each of the 4 D2RA Pathways and develop a plan as to how it will address gaps/capacity shortfalls, in order to maximise D2RA potential locally
4.3 | Local commissioning for implementation of the 4 D2RA Pathways should reflect the output of the national ‘Right-Sizing Community Services for Discharge’ project
4.4 | Local work will be required to engage local care home providers in the implementation of D2RA Pathway 4, using the ‘What Good Looks Like’ Guidance
4.5 | Work with collaboratively with WAST and other providers, to develop a range of transport options to facilitate timely transfer and discharge

## Theme 5
Theme 5: Community Step Down Capacity
Progress on Planned Next Steps
No: | Action | Assessment of current position (September 2019) - baseline current state (e.g. Point in time measurement: Numerical and contextual) | Outline of proposed next steps for winter 2019/20 - future state (e.g. what is it you are going to change? May include multiple step, specific & measurable) | What are your expected Benefits and Impact* (e.g. based on current state/hypothesis) | How are you going to measure? (e.g. what measurement are you going to use to prove it? Qualitative and quantitive measures) | Partners involved | Improvement category (please select relevant category from drop down menu) | Areas of good practice (e.g list areas which could be shared nationally) | National support required (e.g. from National Programme teams) | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01
5.1 | Demand and capacity analysis resulting in an action plan (see right-sizing community services work)
5.2 | Implement National guidance on ‘What Good Looks Like’ for D2RA Pathway 3 (to be published in September) to support HB implementation (NPUC Delivery Unit project)
5.3 | Avoid spot purchasing individual beds in care homes and block commission specifically for step-down care
5.4 | Jointly commission the right service provision
5.5 | Each HB must deliver a plan as to how it intends to adapt and resource therapy and activity input into community hospitals

## Theme 6
Theme 6: An enhanced focus on the respiratory pathway
Progress on Planned Next Steps
No: | Action | Assessment of current position (September 2019) - baseline current state (e.g. Point in time measurement: Numerical and contextual) | Outline of proposed next steps for winter 2019/20 - future state (e.g. what is it you are going to change? May include multiple step, specific & measurable) | What are your expected Benefits and Impact* (e.g. based on current state/hypothesis) | How are you going to measure? (e.g. what measurement are you going to use to prove it? Qualitative and quantitive measures) | Partners involved | Improvement category (please select relevant category from drop down menu) | Areas of good practice (e.g list areas which could be shared nationally) | National support required (e.g. from National Programme teams) | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01
6.1 | Assess if Immunisation Champion for Respiratory Medicine is appointed and this is reflected as a priority in the job plan
6.2 | Assess primary care cluster risk stratification of respiratory groups and identify best practice
6.3 | Primary care clusters to audit the influenza vaccine call and recall system for those with chronic respiratory disease and report on percentage with robust systems in place
6.4 | Assess current information provided to respiratory patients across healthcare system
6.5 | Review 2018/19 staff vaccination rates in Respiratory Team (who should be exemplars for the service)
6.6 | Assess number of community pharmacy engagement in 2018/19 flu campaign and their contribution to raising awareness of need for flu vaccination in those on repeat prescriptions for inhaled steroids

## Theme 7
Theme 7: An enhanced focus on the frailty pathway
Progress on Planned Next Steps
No: | Action | Assessment of current position (September 2019) - baseline current state (e.g. Point in time measurement: Numerical and contextual) | Outline of proposed next steps for winter 2019/20 - future state (e.g. what is it you are going to change? May include multiple step, specific & measurable) | What are your expected Benefits and Impact* (e.g. based on current state/hypothesis) | How are you going to measure? (e.g. what measurement are you going to use to prove it? Qualitative and quantitive measures) | Partners involved | Improvement category (please select relevant category from drop down menu) | Areas of good practice (e.g list areas which could be shared nationally) | National support required (e.g. from National Programme teams) | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01
7.1 | Work with clusters to undertake risk stratification of population - electronic frailty index (eFI)
7.2 | Medicines optimisation schemes
7.3 | Development of local integrated, whole system solutions to build resilience for older people with varying degrees of frailty based around personal and community resources
7.4 | Role of ED/Assessment Units and in reach teams to support the admission avoidance agenda. Ensure WAST is engaged in pathways, in particular, access criteria and opening times
7.5 | All ED to set up an acute frailty service/in-reach model to identify and stream people with frailty to receive the most appropriate care quickly (within 1 hour)
7.6 | Freeing up hospital beds and reducing unnecessary hospital attendances and admissions (local solutions to develop Acute Frailty Units including advice/daycase)

## Sheet1
Dropdown menu:
Connecting up the patient journey
Developing the team around the patient journey
Making the patient and care experience central to every stage of the journey
Making sure there is capacity to meet patients’ needs at every stage of the journey