Strategic Programme for Primary Care Fund 2022-2024

Mid-Year Monitoring Report

October 2022

# Executive Summary

- This report covers the first six-month progress of the Strategic Programme for Primary Care (SPPC) Fund 2022-2024 and the 17 schemes allocated investment from the programme.

- This investment was established out of the repurposing of the National Pacesetter Programme.

- Five of the schemes commenced during Q1 and Q2 with a further eight reporting to start during Q3 or Q4. A small number of schemes have not reported a start date. The majority of schemes with delayed or no start date tend to be the schemes to support obesity prevention.  Consideration regarding duration of schemes and start dates should be built into future transformation investment programmes. (Appendix 2)

- Not all schemes reported financial information requested. From those that did, a total spend of £369,163 was reported for Q1 and Q2 with an estimated year end spend of £2,445,929 and a potential underspend of at least £356,495. (Table 2)

- Some schemes that have already identified an underspend have reported that this will be diverted to support the implementation of the ACD programme and infrastructure. No details of what this will cover were provided.

- The majority of the schemes have reported progress against objectives at six months. The ones that have reported limited or no progress are the small number of schemes yet to commence.

- Generally, all schemes have reported some degree of regular local monitoring and / or reporting. Only two schemes reported to be planning for an end of scheme evaluation with one further scheme seeking advice from the Primary Care Division, Public Health Wales. Governance and evaluation regarding end of programme reporting of individual schemes and the programme as a whole to be able to understand the learning from the investment need to be considered now for the end of year report.

- Key learning indicate broad themes of communication, delays in commencing the work, timeliness of contract changes, changes to what was planned for delivery and opportunities for the ACD implementation related schemes. For the obesity related schemes, themes of recruitment challenges have hampered progress, underestimation of time needed for training, primary care priorities and pressures, digital solutions, procurement issues, changes to what was planned for delivery and opportunities were reported.

Contents

Executive Summary	2

1.	Introduction and background	4

2.	Purpose	4

3.	The schemes	4

3.1 Table 1 – Duration of the schemes	4

4.	Progress	5

4.1   Start date	5

4.2   Progress against individual scheme objectives	5

5.	Summary of spend against allocation	5

5.1 Table 2 - Health Board allocation and spend 2022-2024	6

6.	Plan for reporting / evaluation	6

6.1 Schemes to support the implementation of the ACD Programme	7

6.2    Schemes to support obesity prevention	7

7.	Key learning	7

7.1    Schemes to support the implementation of the ACD Programme	7

7.2    Schemes to support obesity prevention	8

Appendix 1 – Health Board reports	10

Table 3 - Individual Health Board Mid-Year (6 month) update report	10

Appendix 2 – Details and duration of the schemes	11

Table 4 - Details, start dates before 30/09/2022 & duration of schemes supporting ACD implementation	11

Table 5 - Details, start dates before 30/09/2022 & duration of schemes to address obesity prevention	12

Appendix 2 – Progress reported to September 2022	13

Table 6 - Progress of schemes to support ACD implementation by health board	13

Table 7 - Progress of schemes to address obesity prevention by health board	15

# Introduction and Background

The National Primary Care Fund was established in Wales in 2015 to support the delivery of Our Plan for a Primary Care Service for Wales up to March 2018.  As a result the Pacesetter Programme was established in 2015 to provide a systematic approach to testing and evaluating new and innovative ways of working and where similar schemes are identified across Wales, they will work together to test innovation in a number of themed areas.

Every year, Welsh Government invests £3.8m of the £40m Primary Care Fund in the national programme. Funding is allocated recurrently to health boards across Wales and its use is collectively agreed via the national Directors of Primary and Community Care (DPCC) Executive Peer Group, endorsed by the National Primary Care Board and ratified by Welsh Government.

For 2022-2024, the National Pacesetter Programme revenue funding stream has been relaunched across Wales as the Strategic Programme for Primary Care Fund (SPPC Fund). This programme commenced in April 2022 with agreement that the Fund is to be used in 2022/23 by health boards to support the implementation of the Accelerated Cluster Development Programme (ACD) and investment into primary care schemes to support obesity prevention, aligned with the Healthy Weight Healthy Wales Strategy. These two investment areas were agreed by the Directors of Primary Care Peer Group and endorsed by the National Primary Care Board in February 2022.

Information on all the SPPC Funded schemes and original proposals can be found on Primary Care One.

# Purpose

The purpose of this paper is to provide a six-month position to the progress made against the schemes from the SPPC fund investment.

# The Schemes

A total of 17 proposals were agreed for investment for 2022-2024.

- Seven schemes  to support the implementation of ACD across six health boards.

- Ten schemes  to address obesity prevention across seven health boards.

The reported duration of the 17 schemes is illustrated in the table below.

## 3.1 Table 1 – Duration of the schemes

| Duration | Number of schemes | ACD schemes | Obesity schemes |
| --- | --- | --- | --- |
| 2 years + | 1 | 1 | 0 |
| 2 years | 7 | 1 | 6 |
| 15 months | 1 | - | 1 |
| 1 year | 6 | 4 | 2 |
| TBC | 1 | 1* | 0 |
| Not reported | 1 | 0 | 1 |

* Assumption made by the financial allocation reported this will be for 1 year.

One ACD scheme identified investment for a two-year period and a further scheme reported the scheme will continue beyond 2023 (2 year+ duration).

Only two of the schemes to support obesity reported to start on the planned start date and only one of these was during Q1/Q2.  It is unlikely that other than the two aforementioned schemes, none of the other schemes to support obesity will run for the full duration according to their planned end dates and the date of the end of the SPPC Fund Programme.

# Progress

## 4.1   Start date

Of the 17 schemes agreed for investment for 2022-2024:

- Three started on 1 April 2022 (all ACD)

- Two reported a delayed start in Q1/Q2

- Eight reported as not started (as at 30 Sept 2022)

- Four have not reported a start date

Details are provided in Appendix 1.

## 4.2   Progress against individual scheme objectives

The majority of schemes reported to be making progress against the objectives initially set for the proposal. These tended to be actions relating to:

- Establishing foundations for delivery later in the year e.g. establishing groups and meetings, exploring models, OD support and further bids for funding,

- Communication and engagement activity,

- Building on or reviewing what is already in place e.g audit, expanding provision,

- Recruitment and training,

- Commissioning selective pieces of work,

- Making connections with relevant organisations or part of the system, and

- Identifying data needs.

Schemes reporting no or limited progress are those that have yet to commence fully:

- Pre-Diabetes brief interventions at Cluster level (CVUHB)

- Pre-Diabetes Early Intervention Programme (PTHB)

Details are provided in Appendix 2.

# Summary of spend against allocation

Spend at the six-month point (30 September 2022) was reported for 16 of the 17 schemes. One scheme provided no financial details.

Four of the 17 schemes reported zero spend during Q1 and Q2.  Those that did report to have spent some of the SPPC Fund allocation during Q1 and Q2 (n=12), report a total spend of £369,163.

Due to the lack of financial information reported by some schemes it is not possible to report accurately at this time a projected year end position and therefore programme under/ overspend for 31 March 2023.

Using the information provided by the schemes that have reported financial information an estimated year end spend could be in the region of approximately £2,445,929 with a potential underspend of at least £356,495.

Most of the reported underspend appears to be with the schemes to support obesity prevention. Three obesity schemes reporting an underspend have suggested that this will be used to support ACD implementation.

## 5.1 Table 2 - Health Board allocation and spend 2022-2024

| Health Board | HB Annual allocation1 | Scheme | Year 1 Budget | Spend to 30 Sept 2022 | Forecast year end spend | Under / overspend | Comment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ABUHB | £715,000 | ACD | £561,491 | £95,342 | £534,996 | -£16,495* | - |
|  |  | Weight management | £153,509 | £5,571 | £153,509 | £0 | - |
| BCUHB | £840,000 | ACD | £594,424 | £5,950 | £594,424 | £0 | - |
| BCUHB |  | Systems Approach to Population Health Management | £138,604 | £0 | Not reported | Not reported | - |
| BCUHB |  | Digital program to enable virtual group pathways for Type 2 diabetes | £106,972 | Not reported | Not reported | Not reported | - |
| CTMUHB | £575,000 | Inverse Care Law Programme | £573,099 | £25,000 | Not reported | -£250,000 | - |
| CVUHB | £537,000 | Pre-Diabetes scheme | £70,000 | £2,000 | £26,000 | -£44,000 | Underspend will be diverted to ACD programme and infrastructure costs |
| CVUHB |  | ACD | £350,000 | £24,000 | £350,000 | £0 |  |
| CVUHB |  | Living Well | £57,000 | £2,000 | £35,000 | -£22,000 | Underspend will be diverted to ACD programme and infrastructure costs |
| CVUHB |  | Get Cooking | £60,000 | £2,000 | £36,000 | -£24,000 | Underspend will be diverted to ACD programme and infrastructure costs |
| HDUHB | £488,000 | ACD | £71,000 | £0 | £71,000 | Not reported | - |
| HDUHB |  | Healthy Lifestyle Management | 341,000 | £0 | Not reported | Not reported | - |
| HDUHB |  | Community Pharmacy Weight Management | 76,000 | £0 | Not reported | Not reported | - |
| PTHB | £172,000 | ACD | £114,000 | £41,800 | £114,000 | £0 | - |
| PTHB |  | Pre-Diabetes Programme | £58,000 | £3,500 | £58,000 | £0 | Additional £30,000 Cluster Funds allocated to this scheme |
| SBUHB | £473,000 | ACD | £303,000 | £124,000 | £303,000 | Not reported | - |
| SBUHB |  | Diabetes prevention | £170,000 | £38,000 | £170,000 | Not reported | - |
| TOTAL | £3,800,000 |  | £3,798,099 | £369,163 | £2,445,929 | £356,495 |  |

1Allocation figures taken from ‘Pacesetter Programme 2020/22’ letter from Judith Paget to Alex Slade, February 2020

*This was the underspend figure reported by the ABUHB against this scheme however the calculations would suggest that this has been underreported by £10,000 and the actual underspend is £26,495

# Plan for reporting / evaluation

The majority of schemes reported to be planning for local monitoring or reporting. Reporting tends to be monthly via internal governance structures with one health boards reporting weekly monitoring and reporting.

Plans for final evaluation were limited.

- Only two schemes reported to be planning for a final evaluation (ABUHB, CTUHB)

- One scheme accessing advice from PCD regarding evaluation support. (BCUHB)

- Two schemes did not report any plans for monitoring or evaluation (HDUHB)

Governance from a national point of view regarding end of programme reporting of individual schemes and the programme as a whole need to be considered. Plans for the end of year evaluation of each individual scheme does not appear to be in place at present.  An end of year evaluation for each scheme will enable understanding and learning from the investment. This needs to be considered now by health board teams for the end of year one and discussed with Strategic Programme Board as appropriate.

## 6.1 Schemes to support the implementation of the ACD Programme

For schemes to support the implementation of ACD the following examples of reporting, monitoring or evaluation were given:

- Use of the ACD Readiness Checklist monthly, through the local ACD Implementation Group.

- Development of a benefits realisation plan containing system level criteria to monitor progress based on the theory of change and report to the local Programme Board to scrutinise delivery and outcome progress.

- Monthly reporting via Health Board Primary Care Senior Team and bi-monthly to Health Board Primary Care Clinical Board

- Regular progress updates to wider UHB/Executive Committees as part of IMTP monitoring/delivery.

- Progress, monitoring and / or evaluation to commence once post holders are in place.

- Through regular 121s with the ACD Manager and reporting into the Locality Leads meeting.

- ACD action plan based on Ministerial milestones and RAID log monitored and updated weekly and reported to formal project board (meets weekly) with reporting through to the Executive Management Board.

- Informal meeting with cluster leads.

6.2    Schemes to support obesity prevention

For schemes to support obesity prevention the following examples of reporting, monitoring or evaluation were given:

- Monthly monitoring process in place via flash reports, bi-monthly reporting to PCIC Clinical Board

- Monthly meetings with cluster representative to inform reporting reflecting the requirements of the All-Wales Diabetes Prevention Programme reporting format.

- The development of an evaluation framework for the programme. This will include process and outcome indicators.

- Work with the Local Public Health Team (LPHT) to develop the evaluation/service review with the option to approach an evaluation partner if capacity is an issue in the LPHT.

- Access support from PCD regarding evaluation.

- Ongoing monitoring and evaluation through steering group.

- Full AWDPP project plan and project board established with alignment of measures to PHW National AWDPP programme.

# Key learning

## 7.1    Schemes to support the implementation of the ACD Programme

A number of schemes reported several issues that were either unintended or unexpected or health boards would have hoped to have achieved within the first six months of the programme. These included:

- Communication to the service about availability of funds to support ACD implementation

‘It has been challenging when SPPC events inform colleagues of monies allocated for ACD, without acknowledging the wider commitments HBs have made against the funds.’

- Delays in commencing the work caused by a variety of reasons is having an impact on the schemes and for some schemes the timescales of deliverables

‘With resources being delayed in commencing, the deliverable timescales have reduced to 18 months’

‘Progress in relation to governance alignment has not progressed as swiftly as we had anticipated. Further communication efforts are required with some key stakeholders to enhance engagement.’

‘Delays in recruitment to the NCN office has resulted in a delay in the implementation of the programme work streams. The organisation development component of the programme …has been commissioned externally due to delays in recruitment.  The balance of the NCN office has been adapted to reflect the support required to establish the professional collaboratives.’

‘Recruitment has been slow to advance – however, we are hoping to be able to appoint a number of posts internally to support this work.’

- Timeliness of contract changes to enable remuneration for protected time for professional collaborative activity has delayed progress of local collaborative development.

‘Dental Collaboratives have been more difficult to establish as an engaged workforce as it continues to sit outside of their contract.’

- A few schemes changed what they planned to deliver

‘We are in the process of commissioning a full induction, training and OD package for Clusters and Collaboratives, which will use much of the slippage. We are also working through the implications of the nationally proposed ‘offer’ to collaborative and cluster leads, in terms of remuneration. Again, it is anticipated that this will use a considerable proportion of the current slippage.’

‘Potential to consider funding to support professional collaborative development from scheme slippage where the contract does not support e.g., dental’

‘Vacancies in LCC posts and resignation of administration posts’… [have affected deliverables].

- Opportunities that have been identified

‘Based on the work undertaken to date we are likely to consider extending the ACD Manager role as a substantive post as the work cannot be completed within a short timescale and will need ongoing oversight and management to ensure successful outcomes.’

‘Identifying potential for more professional collaboratives to be formed at Health Board level. Meetings arranged with the Community Dental Service and Mental Health directorate.’

## 7.2    Schemes to support obesity prevention

- Recruitment challenges have hampered progress

‘Challenges in recruitment and the recruitment process overall due to delayed advertising and on-boarding processes now taking over 90 days. There have also been some delays sourcing IT equipment.’

‘Not all staff recruited within expected timeframe due to issues with initial JDs…. limited support for nurse led clinics and CPD/QA from other staff.’

‘…cluster workforce recruited and withdrew at end September.  Restart of recruitment has been implemented.’

- The time needed for training was underestimated

‘Staff member in post and undertaking training.’

‘Because of delays in the required training availability for the HCSW, the Cluster have been unable to commence the programme fully.’

‘…spend has been minimal, due to delays in formal training.’

- Primary care priorities and pressures

‘Delay to programme start due to reluctance from practice to start new services during the flu season and end of year QAIF reporting.’

- Digital solutions

‘Scoping the current available digital offerings available to NHS Wales that the project can access as part of the whole project (and the anticipated use in practice at scale) has not been intuitive and straightforward. However, the information and contacts found have offered insight into possible solutions not anticipated and so will reduce replication or time on work direction unlikely to be practical.’

- Procurement issues

‘The requirement to put the project through the Procurement process despite it being an existing scheme has caused delays’

‘Procurement of service and further internal debate on the correct model has stalled commissioning.  Plan now in place to go out to procurement for a service provider.’

- Opportunities that have been identified

‘Good links developed with Integrated Wellbeing Network leads identified and local authority healthy eating plans in Caerphilly where co-working with the community dietetic team can be supported.’

‘Although not able to commence the programme fully, some of the practices, which had previously delivered a LES Lifestyle service, and a previous Diabetes LES,  a number of years ago, where there are some similarities between the AWDPP and the previous LES services, the practices have been able to utilise skills they had as part of these, in the proactive management of patients, whilst they await the training, and formal full implementation of the AWDPP service.’

‘Linking with Diabetes UK on the workstream of training HCP on remission has supported programme development and is consistent with national strategic direction and reduced work required in that aspect through collaboration.’

- A few schemes change what they planned to deliver

‘No longer pursuing a [health board] website as an All-Wales website for level 1 support is being created with portals to each HB site.’

‘To note any underspend accumulated from delays in other projects will be utilised to support the ACD infrastructure.’

‘The requirement to procure the service [Primary Care Led Healthy Lifestyle Management] rather than expand an existing model’

# Appendix 1 – Health Board reports

## Table 3 - Individual Health Board Mid-Year (6 month) update report

| Health Board | Mid-Year Update report |
| --- | --- |
| Aneurin Bevan UHB |  |
| Betsi Cadwalader UHB |  |
| Cardiff and Vale UHB |  |
| Cwm Taf Morgannwg UHB |  |
| Hywel Dda UHB |  |
| Powys THB |  |
| Swansea Bay UHB |  |

# Appendix 2 – Details and duration of the schemes

## Table 4 - Details, start dates before 30/09/2022 & duration of schemes supporting ACD implementation

| Health Board | Title of Scheme | Description of Scheme | Investment | Duration of the scheme | Start date | Planned end date | Explanation of delay in start |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Aneurin Bevan UHB | Accelerated Cluster Development Hub | The aim of this project is to strengthen planning and deliver through Clusters (NCNs) with investment in an Accelerated Cluster Development programme. | (Year 1) £561,491 (Year 2) £426,306 | 2 years | 05/05/2022 | Not reported | Using matrix management approach to enable ACD sustainability |
| Betsi Cadwalader UHB | Embedding and Maturing Accelerated Clusters across North Wales | It is recognised that partners will require additional support and resources to help them move forward with the ACD agenda, and implement Pan Cluster Planning Groups, and ensure the appropriate governance, leadership and systems are in place to provide a platform for integrated place-based working. | £594,424 | TBC | Not reported | 31/03/2023 (6-month reports suggests 31/03/2024) | Recruitment to the posts has been significantly delayed, however, we anticipate recruitment to commence within the next 4 weeks |
| Betsi Cadwalader UHB | Developing a (Digital) Systems Approach to Population Health Management | This proposal seeks to work with partners across primary care, community health, social care and public health, to agree the types of population data that is needed to support effective Cluster planning. Where that data is not currently being collected, or is not collected within the appropriate timescales, mechanisms will be developed to support its collection. | £138,604 | 1 year | Not reported | 31/03/2023 | N/A |
| Cardiff and Vale UHB | ACD Infrastructure | To enhance the planning and delivery capabilities of collaboratives as part of the ACD programme. | £350,000 | 1 year | 01/04/2022 | 31/03/2023 | N/A |
| Hywel Dda UHB | ACD Programme Support | The funding will be used to support Clinical Leadership and project management support to scoping, developing and implementing ACD within Hywel Dda. | £71,000 | 1 year | 10/2022 | 31/03/2023 | Delay due to recruitment into ACD Manager and Clinical lead posts |
| Powys Teaching HB | Accelerated Cluster Model Development | To strengthen the Cluster model of working across North and Mid Powys, with the objective of delivering a strategically clear, robust, proactive, and cohesive cluster delivery model. | £114,000 | 1 year | 04/2022 | Not reported | N/A |
| Swansea Bay UHB | ACD Development Programme | To implement Accelerated Cluster Development Programme across SBUHB. | £303,000 | 2 years + | 04/2022 | Beyond April 2023 | Will continue beyond April 2023 as full implementation will require a longer embedding period. Results of National review & lessons learnt will be key to this. Mainstreaming process will continue throughout 23-24 |

## Table 5 - Details, start dates before 30/09/2022 & duration of schemes to address obesity prevention

| Health Board | Title of Scheme | Description of Scheme | Investment | Planned duration | Start date | Planned end date | Explanation of delay in start |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Aneurin Bevan UHB | Weight Management Brief Advice and Self-Directed Support in Primary Care | The aim of this project is to ensure systematic provision of brief advice, signposting and access to self-directed support for achieving or maintaining a healthy weight (step-down). | (Year 1) £153,509 (Year 2) £288,694) | 2 years | 01/09/2022 | 31/03/2024 | 18 months due to delayed start date with recruitment. |
| Betsi Cadwalader UHB | Digital Programme for Type 2 Diabetics | The development and operation of an on-line learning space that enables ease of access, and optimal teaching support, plus facilities for people with diabetes who wish to lose weight using VLCD (initially, plus further development thereafter) to improve their long-term health outcomes. | £106,972 | 1 year | Not reported | 31/03/2023 | No current delay - the tender process to procure relevant software date of full completion is not yet known |
| Cardiff and Vale UHB | Pre-Diabetes brief interventions at cluster level | To provide brief intervention programme to patients identified as pre-diabetic by a trained support worker, supported by a dietitian. | £70,000 | 15 months | Q4 2022/23 | 31/03/2024 | Scheme not planned to start until Q4 2022/23 |
|  | Living Well | This cluster-based project will deliver Foodwise for Life and Escape Pain as well as other activity sessions to patients to support obesity management at a cluster level. | £57,000 | 2 years | 10/2022 | 31/03/2024 | Scheme likely to run for 18months |
|  | Get Cooking | 7-week practical cooking course for community members including carers. The dietitian will train and supervise the support worker to deliver a range of healthy eating initiatives with community groups | £60,000 | 2 years | TBC | 31/03/2024 | Recruitment delays due to need to undertake local job matching. |
| Cwm Taf Morgannwg UHB | Enhanced Inverse Care Law Programme | This proposed programme will focus on further developing, aligning and initially bringing together the following services: - Inverse Care Law Health Check Programme - Prevention Health Checks for Patients with serious mental illness - The All-Wales Weight Management service - Wellness Improvement Service & - Education Patient Programme - All Wales Pre-Diabetes Prevention | (Year 1) £575,000 (Year 2) £575,000 | 2 years | 11/2022 | 31/03/2024 | Delay due to reluctance from practice to start new services during the flu season and end of year QAIF reporting |
| Hywel Dda UHB | Primary Care Led Healthy Lifestyle Management | Amman Gwendraeth Cluster Lifestyle Clinic: The programme looks at all aspects of lifestyle including food, sleep, stress management and exercise with advice on habit formation. There are between 10 and 12 people in each group with each group running for 8 weeks. The programme is led by a local GP. | £341,000 | 2 years | Not confirmed | 31/03/2024 | Delay will result in the programme running for a shorter period of time than anticipated |
|  | Community Pharmacy Led Weight Management | Working with either Slimming World or WW to commission packages of 12 weeks support for patients who are identified by a Community Pharmacist as being diabetic and wanting to lose weight. | £76,000 | 2 years | To be confirmed | 31/03/2024 | Will run for a shorter time period |
| Powys Teaching HB | Diabetes Prevention Early Interventions | The programme follows the All Wales Pre-Diabetic Prevention Programme piloted by Afan Valley and North Ceredigion clusters, the project aims to improve the prevalence of type 2 diabetes in the South Powys population by supporting the introduction of a robust prevention and intervention pathway for patients who are or at risk of developing diabetes. | £58,000 | 1 year | 11/2022 | 10/2024 | Delays in training availability for the HCSW. |
| Swansea Bay UHB | Diabetes Prevention | To deliver diabetes prevention interventions in additional 3 clusters in SBUHB. | £170,000 | Not reported | Not reported | Not reported | The duration of scheme has not changed - this is a recurrent scheme x 3 Clusters for AWDPP |

# Appendix 2 – Progress reported to September 2022

## Table 6 - Progress of schemes to support ACD implementation by health board

| Health Board | Title of Scheme | Achievements against objectives to 30 September 2022 |
| --- | --- | --- |
| Aneurin Bevan UHB | Accelerated Cluster Development Hub | Objective 1 - Initial set up of the programme commenced beginning of May 2022 with commitment of supporting: - Updating existing governance structures to reflect PCPG functions being adopted by existing Integrated Service Partnership Boards (ISPBs) at Borough level - Establishment of professional collaboratives - Establishment of NCN office structure and team - Ongoing reform of the ISPBs, with emphasis on TOR and membership. - Workstreams have been implemented through existing partnership forums with multi-agency and multi-professional stakeholders across health and care. SRO presented at the RPB Leadership Group on 17th August and provided a progress update on NCN development programme. Proposed governance process for planning and delivery of joint programmes and plans through ISPBs which have been informally endorsed by RPB. Discussed and agreed to proceed with ISPB development sessions commencing in October. The ISPB sessions will be facilitated by PCC. Thereafter, the proposed Joint Planning Framework and governance arrangement will be presented at the Board Strategic Planning Session on 19th Oct, and following this, there will be formal ratification at ABUHB Public Board meeting in November. Objective 2 - We have agreed a series of milestones for the NCN plan refresh through an updated Population Needs Analysis and Joint Planning Framework to enable: - Annual update of current NCN plans and production of the ISPB 3-year plans - Reflect on what has been delivered and will be delivered by end of year, what has changed and what is on the horizon - PNA quick reference guide to support planning process and identification of priority areas based on population need - Incorporation of insights from thematic and collaborative leads - Revisions based on WG planning guidance - NCN plans will be reviewed on a Borough basis by the ISPBs prior to plan submission to ensure strategic alignment. IPSB 3-year plans will be submitted to WG in line with Ministerial milestones. Objective 3 - The programme team has been appointed under a matrix management arrangement, with the intention that the support for NCN development becomes embedded within the organisation structures. We have established a Programme Board represented by health Board and Local Authority representative at Exec/Associate Director level with the intention of influencing, steering and securing resources required to deliver the programme outcomes. Through workforce and development, we have commissioned external resource to facilitate discussions centered on purpose and delivery mechanisms between RPB and ISPB planning and delivery. |
| Betsi Cadwalader UHB | Embedding and Maturing Accelerated Clusters across North Wales | Whilst recruitment has been delayed, achievement against key objectives has progressed: - PCPG and Cluster meetings in place with ToRs agreed and signed-off in Conwy and Denbighshire - Final arrangements underway for sign-off in East (Wrexham and Flintshire) and Anglesey (awaiting Director appointment in Gwynedd in order to proceed) - Commissioning of specialist suite of training & OD support for Clusters and Professional Collaboratives and Leads, underway - Pan-north Wales Cluster bids submitted for IMTP investment – if successful, this will free up Cluster Funds for multi-agency/ professional projects in 2023/4 |
| Betsi Cadwalader UHB | Developing a (Digital) Systems Approach to Population Health Management | - ACD and Primary Care workshop helped to start the discussion over the data needs of clusters/ pan-cluster planning groups - Agreement from Informatics and Performance teams to lead on this programme of work on behalf of clusters/ pan-cluster planning groups - Project plan developed and awaiting appointment of key posts |
| Cardiff and Vale UHB | ACD Infrastructure | - Professional Collaborative Working group in place - Delivered ACD briefing sessions to; - LDC - SEWROC - Community Pharmacy PCCLs - Optometry practices - X3 Engagement events undertaken with Dental and optometry practices across Cardiff and Vale - Formal invite to form as professional collaboratives to be shared mid-October - Local engagement with AHP and Nursing Collaboratives undertaken/continuing to support groups to form |

| Health Board |  | Title of Scheme | Achievements against objectives to 30 September 2022 |
| --- | --- | --- | --- |
| Hywel Dda UHB | ACD Programme Support |  | ACD Manager in post and work on establishing professional collaboratives has started. Advert for clinical lead ready for advertisement. |
| Powys Teaching HB | Accelerated Cluster Model Development |  | Progress milestones for Q1 & Q2 include: - Review of the current model and purpose was undertaken, in Q1, through engagement with Cluster Leads and Health board representatives, with a view to establishing the existing and future vision for Clusters. - ACD Information and Q&A sessions were delivered within Q1 & 2, to GMS contractors, Pharmacy, Optometry, & 3rd Sector Cluster representatives. with additional PLT’s organised for all 3 Clusters, which identified an appetite for change from the old model. - A shared understanding, of the purpose and vision for the Clusters, aligned to the national vision has been agreed and adopted, across Cluster representatives, 3rd sector, Collaboratives, Health board and RPB. - A Powys Cluster delivery model has been developed and agreed for the transition year. - New structure of the Cluster and Collaborative Groups has been launched September, based on the national model. - Engagement with Optometry and Dental contractors is in place to establish the shared vision and purpose for Clusters with newly created Collaboratives ensure that there taking place. |
| Swansea Bay UHB | ACD Development Programme |  | - Majority of workforce recruitment completed to support ACD implementation. - Agreed and implemented SBU Governance Framework for ACD including arrangements for PCPG reporting. - Established/Supported Professional Collaboratives for :- GMS x8; Pharmacy x8; Optometry x2; Dental x4; AHP x1 regional, Nursing Collab x1 regional. - Reviewed, updated and agreed all TORs, secured PCPG membership, realigned Cluster membership and structure to now become Local Cluster Collaboratives x 8. - Agreed single PCPG for the region. Held initial Shadow/Workshop style PCPG in June 2022 and first Formal PCPG in September 2022. - RPB (via Regional team) engagement with ACD development programme through dedicated task and finish group. - Dedicated Comms officer for ACD appointed, draft communication plan agreed, and formal patient/public engagement plan will be developed SPPC Fund 2022 Page 4 of 5 following a review of existing arrangements. - Agreed joint priority areas (PCPG) for 2023/24 plan development. - Agreed timeline for PCPG Plan - Maintained delivery of 2022/23 Cluster IMTPs whilst looking forward to 2023/24 and beyond. - Training Needs Assessment process to support leads and address any knowledge/skills gaps. This is linked to SPPC Organisational Design and HEIW training materials. - Nominated a LCC and representatives for cluster peer group review. - Key members of the ACD implementation team have attended the CIC workshops to develop knowledge of potential delivery models. - Ministerial Milestones - Completed or working on achieving (see separate report). No report provided in Mid-Year return. |

## Table 7 - Progress of schemes to address obesity prevention by health board

| Health Board | Title of Scheme | Achievements against objectives to 30 September 2022 |
| --- | --- | --- |
| Aneurin Bevan UHB | Weight Management Brief Advice and Self-Directed Support in Primary Care | Objective 1 - ABUHB have been working with PHW on the development of the national HW:HW website. This will replace need for a local ABUHB website. The Health Board Communications team has met with the Healthy Weight team to discuss current position across Gwent for weight management, priority audiences, current behaviours and desired interventions. The communications team have taken away the information to produce a Communications and Marketing strategy to support priorities for Level 1 Weight Management locally. This will include an all-Wales audit of the Level 1 weight management offer in other Health Boards in terms of communication products and self-directed resources. Initial communication priorities will include: - Establishment of a local website hub for information, signposting and resources for the population of Gwent - Audit of current resources and refreshing of resources if needed - Commissioning of a PR agency to explore a local PR campaign to raise awareness of the importance of Healthy Weight with relevant signposting to self-help resources - Exploration of local opportunities to relieve pressure on Level 2/3 services through other avenues of support across Gwent The above will also incorporate any national activity which will be used as a springboard to support local campaigning. Dietetics website to be updated to provide a description of Level 1 provision, known locally as the Community Health Programme along with contact details. Online resources and self-help material will be linked to this site. Objective 2 - Service Lead (Band 7) has been appointed and work is underway updating and developing resources for the healthy weight element of brief advice training. Objective 3 - Venue scoping for the community-based initiatives has begun to ensure the role out of the Community Health Programme can commence in the next quarter. Co-working has begun with the Integrated Well-being Network leads in Blaenau Gwent & Caerphilly to ensure the Community Health Programme team will have good links to sign posting of local services to support behaviour change. Training booked as part of induction for 3 x Assistant Practitioners including MI training booked with Association for Psychological Therapies & Community Nutrition Support Training within ABUHB. Objective 4 - Co-working with DPP project for Lifestyle Adviser (Band 4) staff has begun to ensure integrated working across both programmes to enabling appropriate access to support across the Diabetes Prevention Programme, Adult Weight Management Service and the Community Health Programme. |
| Betsi Cadwalader UHB | Digital Programme for Type 2 Diabetics | - Procurement contact established to begin process. - Recruited to an amended staff allocation based on what we can resource in house with the particular skill set required for duration of project (including re-allocation of clinical commitments to other team members. Recruiting is complete and new staff are in post for project administrator and health practitioner / nutritional support programme practitioner - Scoping complete for: - QISMET accreditation. Product development evaluated so-far is in keeping with the requirements for full accreditation of the programme as set out by QISMET and in line with NICE guidance for structured education - Project link & collaboration with the National Diabetes UK (DUK) strategic Healthcare professional education digital module for Remission of Type 2 diabetes. - Secured agreement from DUK to be early implementer testing the feasibility of the training module (above) to support our programme specific training for non-specialist educators - Foundation content for the low-calorie virtual group programme has begun and is on track |
| Cardiff and Vale UHB | Pre-Diabetes brief interventions at cluster level | N/A – Programme has not yet commenced |
|  | Living Well | - HCSW recruited and commenced in post September 2022. - Dietetic & Physio sessions recruited/in place - Training underway |
|  | Get Cooking | - Job description developed and submitted for matching - Exploring options to cross cover work from other streams whilst awaiting recruitment. |
| Cwm Taf Morgannwg UHB | Enhanced Inverse Care Law Programme | - Recruited HCSW’s and Lifestyle Advisors to posts – some still undergoing pre-employment checks - Expanded the ICL team to include additional HCSW’s and Lifestyle Advisors to enhance our health check offer now including AWDPP prediabetes check - Staff undertaking CVD health checks and just due to start in November 22 to deliver the AWDPP intervention – team are social prescribing and referring to appropriate third sector organisations/services to address physical activity, healthy eating, loneliness and isolation - Working with Promo Cymru to understand what our communities want in regard to their health and wellbeing and to understand how they want to access services now and, in the future, - Lifestyle Advisor appointments focused on behaviour change techniques and motivational interviewing to enable patients to make positive lifestyle changes - First prediabetes AWDPP intervention to start in November 22 in North Bridgend and North Cynon clusters - Health checks for patients with SMI development ongoing – development around appropriate invite letter, working with psychologists and patient support to create the most enabling invite offer – in progress - Discussion around improvement to current models and current processes surrounding the health check and lifestyle advisor appointments to ensure ease of access/best outcome measurement - Working groups commenced for SMI and currently understanding the data and QAIF requirements. Engagement with clusters underway and senior leaders. SOP and handbooks developed in line with governance structures - Health Check Steering group established |
| Hywel Dda UHB | Primary Care Led Healthy Lifestyle Management | Not reported |
|  | Community Pharmacy Led Weight Management | Not reported |
| Powys Teaching HB | Diabetes Prevention Early Interventions | - Achievement against objectives and reporting has been minimal, due to the delays in the programme implementation and training of the team. - The AWDPP programme pathway has been introduced into practices, resources confirmed, reporting templates introduced, patient cohorts have been identified, along with Clinic time, and is expected to start fully November 22. |
| Swansea Bay UHB | Diabetes Prevention | - Programme aligned to rollout of PHW funded AWDPP programme. - X3 Clusters funded via SPCC budget - X1 Cluster workforce recruited & commenced clinic Sept 2022 - X1 cluster workforce recruited and currently in Induction/Training phase. Will commence clinics in Q3. - X1 cluster workforce recruited and withdrew at end September. Restart of recruitment has been implemented. - Positive engagement across Clusters - 5 Clusters being funded via (x2 PHW and x3 SPPC) were a contributory factor in the successful business case within the Health Board for all 8 Clusters being funded – including recurrent funding for the x2 PHW clusters at close of that 2-year programme. |

On 31 March 2022 the national Pacesetter Programme closed.  The £3.8m annual funding was re-packaged to support the delivery of the Strategic Programme for Primary Care (SPPC) priorities and work plan and relaunched as the Strategic Programme for Primary Care Fund from April 2022 (SPPC Fund).  Governance for the Fund is still managed via the national DPPC Executive Peer Group and endorsed by National Primary Care Board.