Lead: Alan Lawrie, National Programme Advisor

Author: Kelly King, Project Manager, Strategic Programme for Primary Care

Date: 25 April 2023

Version: Final 1.0

Purpose: Paper to summarise Health Board returns of the Accelerated Cluster Development (ACD) Readiness Checklist, as at 31 March 2023, to conclude reporting against the delivery milestones over the ACD transition year 2022/23.

Strategic Programme for Primary Care

ACD Transition Year Readiness Checklist; updated

position reported as of 31 March 2023

Paper date: 25 April 2023

Contents

Overview	1

Returns	2

Common themes / areas of concern	2

Table 1 - ACD Programme Readiness Checklist: Health Board Actions	4

Table 2 – SPPC response to the national actions	14

# Overview

A Readiness Checklist was developed to support the Transition Year for Accelerated Cluster Development (ACD) 2022/23. This provided Health Board teams a summary of the tasks to be addressed and, importantly, described why these actions were important and the benefits they were intended to deliver.

The Readiness Checklist contains thirty actions for Health Boards with their Local Authority / Regional Partnership Board partners for delivery between 1 April 2022 and 31 March 2023 and sixteen actions for the Strategic Programme team / national partners.  The Checklist allows teams to self-assess local progress and focus further attention as needed.

An early and midway ‘check in’ on progress, with positions as at 31 May and 30 September 2022 respectively, was captured from all health boards across Wales. The progress and positions were summarised in reports and discussed at the Strategic Programme Board (SPB) on 5 August & 4 November 2022 and shared with National Primary Care Board (NPCB) on 19 August & 11 November 2022. Feedback received from the exercise has been positive, with health boards noting it was helpful to see progress and identify areas to continue to address and progress.

It was agreed, as conclusion of the ACD Transition Year 2022/23, a final review of positions and progress, as at 31 March 2023 would be gathered and collated for Strategic Programme Board and National Primary Care Board meeting in May 2023.

This report summarises the updated position of the 30 health board level actions, from all seven health boards, (Table 1) and the sixteen national level actions (Table 2), as at 31 March 2023.

# Returns

Pre-populated checklists from the two previous submissions were issued to Health Boards on 28 February 2023, with a deadline of 12 April 2023 for completed returns. The report summarises the returns received from all seven Health Boards.

# Common themes / areas of concern

The majority of the actions contained in Table 1 are taken from the letter issued from the Minister for Health and Social Services to NHS Chairs, Leaders of Local Authorities and RPB Chairs (dated 24 March 2022) and from the NHS Wales Chief Executive to NHS and Local Authority Chief Executives (dated 30 March 2022).

Whilst some of the action milestone dates for completion during the transition year have slipped, it is recognised that good progress has been made by all health boards and their partners across Wales to progress the implementation of ACD during the 2022/23 transition year.  Routine progress check-ins with Directors of Primary Care have been undertaken at monthly Strategic Programme Board meetings and with the health board Service leads for ACD delivery via the ACD Action Learning Group (ALG) to ‘check-in’ and share learning across Wales.

To note:

From a Health Board perspective:

- All health boards have reported actions #1-4, 16, and 21 as complete.

- Some health boards are still progressing / finalising the governance route, assurance and adopting / adapting the model terms of reference for the Pan Cluster Planning Groups (links to action #5, 6 and 9) with progress being observed across all health board areas following the series of readiness check-ins.

- Health boards teams have progressed with the development of action plans for, and recruitment to, supporting the leadership and OD requirements for the establishment of the various professional collaboratives in their health board area. These discussions and plans are linked to the ongoing contract reform discussions and national leadership programme work led by HEIW / SPPC (links to action #7, 8, 9, 12, 13, 14, 15 and 17).

- Recruitment into posts (action #10) across Wales remains varied with some health boards manging to recruit, others continue to go through the recruitment process, and some health boards are looking to fill posts through possible secondment opportunities.

- Heath Boards have plans in place to ensure that there is good and effective stakeholder, public and patient engagement in Clusters and PCPGs (action #19) and this will be further developed and embedded as the PCPGs mature throughout 2023/24 and beyond. Similarly, discussions continue with RPBs (action #27) to ensure RPB plans are informed by pan-cluster responses.

Whilst significant progress has been made, the ACD Action Learning Group (ALG) has requested that the Readiness Checklist be continued into 2023/24 to ensure that all actions are completed. The ALG provides peer support and opportunities to share solutions to deliver the more challenging tasks. The group plans to review the checklist to retire items that are completed, whilst also considering new priorities for 2023/24.

From a National perspective:

Good progress has been made on the sixteen national actions by the SPPC team:

- The ACD toolkit, Cluster Planning Support Portal, monthly ACD Action Learning Group, PCMW/ACD Peer Review process and the ‘Once for Wales’ APMS Contract and Community Interest Company (CiC) guidance, ACD self-directed learning offer (Gwella) were all delivered during the 2022/23 transition year.

- HEIW have completed work to commission a Leadership Development Programme that includes Action Learning.  The first cohort of 20 Leaders will commence in Spring 2023.

- The action to update the Cluster Handbooks has been deferred to Q1 2023/24.

- Whilst good progress has been made to understand and address Cluster Information Governance requirements, further work is required across the system over the course of 2023/24; to be led by DHWC reporting into the SPPC work stream.

- Good progress has also been made to scope the governance arrangements for PCPG/ACD within Health Board schemes of delegation and into the partnership arena with Regional Partnerships Boards.  A Health Board Supporting Governance paper was produced in Q4 and work will be completed over the course of 2023/24 to update the SS&WB Act Part 9 guidance.

Further discussion and monitoring will proceed over 2023/24 through the ACD Action Learning Group to ensure full delivery of all milestones.

# Table 1 - ACD Programme Readiness Checklist: Health Board Actions

| Green | Complete |
| --- | --- |
| Amber | In progress / partially complete |
| Red | Not started / planned future activity (target not met) |

| Table 1 - ACD Programme Readiness Checklist Actions – Health Board Actions - to be delivered by April 2023 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| # | Timescale | Action | Lead / Owner | Status | Commentary | Why is this important? |
| 1 | April | 2022/2023 Cluster Annual Plans published on Health Board websites (option to hyperlink from PCOne); Health Boards support delivery of the Cluster Plans over the next 12m as required | DPCCs and HB teams | Must do | Completed by all Health Boards Reported as complete by all seven health boards | Plans have been in place for 10 years and should play a central role in informing the Health Board of critical local issues and priorities Plans assist local coordination between teams and services to ensure seamless care and the most efficient use of resources The clarity of existing plans is critical for briefing and engaging the new Professional Collaboratives and Pan Cluster Planning Groups: - To understand where the focus of current effort is placed - To contribute to effective solutions for current challenges |
| 2 | April | 2022/2023 Cluster Funding proposals / initiatives commence; local monitoring in place | DPCCs, PC Teams, Clusters | Must do | Completed by all Health Boards Reported as complete by all seven health boards | Transparency and governance of the use of public money is essential. Spending plans have been in place for seven years but to inform new discussions there needs to be clarity of resource available to support new initiatives The aim of cluster working is to encourage and support collaboration of services around a local community and to test new solutions. This requires clear pathways to test, evaluate and mainstream where projects are successful, releasing resource for further innovation |
| 3 | April | Confirm the geographical boundary to inform the development of the map of Pan Cluster Planning Groups (PCPG) and associated Clusters for the Health Board / Regional Partnership Board region | DPCC, DoP with RPB Partners | Must do | Completed by all Health Boards Reported as complete by all seven health boards | This provides clarity of planning and operational footprints. Leads need to understand the organisational architecture and local decision making systems |
| 4 | April | Agree the governance route within the health board for the Pan Cluster Planning Group | DPCC with DoPs and BS | Must do | Completed by all Health Boards Reported as complete by all seven health boards | This ensures clarity of connection from the RPB to the Cluster footprint and is a key requirement to ensure the effectiveness of the partnership agenda between health boards, local authorities and third sector providers |
| 5 | April (through Q1) | Health Boards and their Local Authority partners establish Pan Cluster Planning Groups, Terms of Reference are adapted / adopted (added to but not downgraded) and PCPG governance is embedded into the local architecture | DPCC, DoP, DSS and RPBs | Must do | Five of the seven health boards report this as complete, with two reporting as ongoing / work in progress across Q1 / Q2 for 2023/24 SPPC Action: Review update / predicted completion date of the two health boards reporting as ongoing / in progress at May Strategic Programme Board (SPB) | The aim of the PCPG is to deliver the principles of the Social Services & Well-being Act 2014 (the Act), The Wellbeing of Future Generations Act (2015) and A Healthier Wales The PCPG will: - Lead the development of an integrated plan which addresses the health, care and wellbeing needs of the whole population of [County] - Support the implementation at local level of the joint partnership agenda, including (but not limited to) - Cluster plans - Integrated [County] plan - Priorities determined by the RPB and the [County] Partnership Board (PSB) - Requirements of the individual organisational plans which involve partnership working - Bring together senior leaders from the NHS, Local Authority (to agree which departments) and key partners in the Third Sector The Cluster Survey highlighted the need for greater influence from Clusters into the wider health and social care system PCPGs also highlight opportunities from time limited to funding streams (such as winter pressures etc) |
| 6 | April-June | PCPG Assurance is part of the Health Boards existing Board Governance structure | BS, DPCC, DoP | Must do | Five of the seven health boards report this as complete, with two reporting as ongoing / work in progress across Q1 / Q2 for 2023/24 SPPC Action: Review update / predicted completion date of the two health boards reporting as ongoing / in progress at May SPB | This ensures that Health Boards are supporting and enabling the business of the Board through the agreed local footprints, informed by the knowledge and experience of the workforce Effective governance structures and processes ensure that HBs understand the maturity of local partnership arrangements and that they put in place appropriate organisational development support PCPGs will be highlighting risks and opportunities from primary and community care services so that HB Governance systems are complete- taking a whole system view that reflects patient, public and workforce experience |
| 7 | April | Set out a project plan to begin establishing the Professional Collaboratives for the contractor professions: GMS, Optometric, Pharmacy, Dental | DPCC, DWOD, Prof Advisors | Must do | Four of the seven health boards report this as complete, with three reporting as ongoing / work in progress with plans in place SPPC Action: Recognised work in progress linked to national Contract Reform. Review update / predicted completion date of the three health boards reporting as ongoing / in progress at May SPB | Clusters were established to support a collaborative approach between ALL local health and social care services serving a defined population The Cluster Survey highlighted that whilst GP practices were established at the core of this approach, the engagement of other contractor services, nursing, AHP, social services and third sector is variable Professional Collaboratives are being introduced to increase workforce engagement. The GP collaborative supports GP practices to address issues specific to General Practice (including sustainability concerns) and similar arrangements apply for the other contractor professions, nursing and AHP Local authorities will consider how similar arrangements might support social care teams. This allows the Cluster to achieve the original aim of a multi-disciplinary forum for holistic needs assessment, collaborative discussions and innovative projects |
| 8 | May | Set out a project plan to begin establishing the comparable arrangements for establishing Professional Collaboratives for other professions such as nursing, allied health professionals, and potentially social services | DPCC, DWOD with DoN, DoTh and DSS | Must do | Three of the seven health boards report this as complete, with four reporting as ongoing / work in progress with plans in place SPPC Action: Recognised work in progress linked to SPPC national/local AHP/Nursing workshops. Review update / predicted completion date of the four health boards reporting as ongoing / in progress at May SPB | As above |
| 9 | April-June | Any changes that are needed to the Health Board Scheme of Delegation / SFIs to allow PCPGs to have delegated authority to act are actioned | BS, DPCC, DoP, DoF | Must do | Two of the seven health boards report this as complete, with four reporting as ongoing / work in progress and one reporting work has not yet started. SPPC Action: Work in progress is linked to actions 4-6 above. Review update / predicted completion date of the four health boards reporting as ongoing / in progress, and planned start date with one health board at May SPB | Ensuring that form follows function – i.e. that systems support and enable the shared purpose PCs and PCPGs will only be successful if they are able to deliver change - they need to be able to respond to local challenges and make the most of local opportunities The decision making process should be transparent, rapid and easy to follow The Cluster Survey highlighted concerns about slow and opaque systems which limit innovation and discourage clinical engagement |
| 10 | April-June | Progress delivery of and appointments to any posts funded from the Strategic Programme for Primary Care Fund 2022 (SPPC Fund) ACD investment plans | DPCCs / HOPC | Must do | Four of the seven health boards report this as complete, with three reporting as ongoing / work in progress – as reported in September ’22, some posts have been recruited to and some recruitment is ongoing and / or secondments being investigated. SPPC Action: Ongoing monitoring via SPPC Fund monitoring | The ACD programme is necessarily ambitious - system backlog, increasing demand and public frustration require an active response Clinical leads need to focus on the clarity of needs assessment, prioritisation, colleague engagement and delivery of solutions They require managerial and technical expertise to deliver this programme of work |
| 11 | April-June | Consider the current Cluster arrangements, membership and governance to ensure it aligns with the model Cluster Terms of Reference for the ACD programme. Review transition year Cluster Lead / Chair arrangements / future Professional Collaborative leads representation on the PCPG | DPCCs, PCPG, and Cluster partners | To Consider | Five of the seven health boards report this as complete, with two reporting as ongoing / work in progress SPPC Action: Recognised work in progress linked to actions 4 – 6 & 9 above. Review update / predicted completion date of the two health boards reporting as ongoing / in progress at May SPB | The Transition Year provides an opportunity to implement and test the ACD actions building on established arrangements and further strengthening the integrated, collaborative approach The ACD Action Learning Group supports this work and provides a forum, with the SPPC, to ensure that there is shared learning, rapid problem solving and effective implementation |
| 12 | May-June | Consider leadership and professional development needs of the various Professional Collaborative Leads and Cluster Leads | DWOD with DPCC, DoN, DoTh and DSS | To Consider | Six of the seven health boards report this as complete, with one reporting as ongoing / work in progress SPPC Action: Review with the health board reporting as ongoing / in progress at May SPB | Clinical Leadership is a critical factor in system change but leads require a clear understanding of the organisational structures and systems and agreed SMART objectives Health Boards must have a clear understanding of their expectations for PCPGs, Clusters and PCs which are articulated to their clinical and managerial leadership HEIW is providing a comprehensive programme of leadership development which can support this work |
| 13 | May-June | Consider the Organisational Development needs to optimise Pan Cluster Planning Group working | DWOD, DoP, DPCC, RPBs and PCPGs | To Consider | Five of the seven health boards report this as complete, with two reporting as ongoing / work in progress SPPC Action: Review with the two health boards reporting as ongoing / in progress at May SPB | As above |
| 14 | May-June | Engage with the SPPC commissioned PCC Leadership engagement exploratory workshops for Professional Collaboratives, Pharmacy, Dental, Optometry, Nursing and AHPs | Primary Care Teams including Nursing and Therapy Leads | To Consider | Four of the seven health boards report this as complete, with three reporting as ongoing / work in progress SPPC Action: Recognised work in progress; review with the three health boards reporting as ongoing / in progress at May SPB | As above |
| 15 | June onwards | Engage with the Strategic Programme for Primary Care on the leadership and OD programmes for Cluster Leads, Professional Collaboratives & Leads PCPG members | DWOD, DoP, DPCC, RPBs and PCPGs, Cluster / Collab Leads | Must Do | Five of the seven health boards report this as complete, with two reporting as ongoing / work in progress SPPC Action: Recognised work in progress; review with the two health boards reporting as ongoing / in progress at May SPB | As above |
| 16 | June | Confirm and prepare one Cluster footprint per Health Board to be part of the Cluster peer review process being drawn up for 2022-2023 | DPCCs / DoPs / RPBs | Must Do | Completed by all Health Boards Reported as complete by all seven health boards | Peer Review provides an opportunity to reflect on the experience of delivering the Cluster approach. This will highlight successes but also clarify challenges and barriers that wider systems can and should address The Transition Year Peer Review cycle will inform the development of an annual process to ensure that this adds value |
| 17 | April-Sept (March ‘23) | Supported by Health Boards, individual Professional Collaboratives are established in each Cluster footprint for General Practice, Pharmacy, Optometry, Nursing, Allied Health Professionals (AHPs) and potentially social services and these are represented on the Cluster / PCPG Subject to contract reform, Dental Professional Collaboratives are expected to be established by March 23 | DPCC, DoPs, WoD, DoTHs, DoNs, and PCPGs, Cluster / Collaborative Leads | Must Do | All seven health boards report as ongoing / in progress with plans in place to take this forward in the areas still in development SPPC Action: Recognised work in progress; review with the health board DPCCs at May SPB following the February ’23 Nursing & AHP workshops and subsequent reports | As above |
| 18 | April-Sept | Update skills and knowledge on the ‘Once for Wales’ contract for PCPGs to use with Community Interest Companies (CICs) if formed | RPBs, PCPGs, HB Exec Teams | Must Do | Six of the seven health boards report as ongoing / in progress, with one health board reporting as complete. SPPC Action: Review any follow-up needed with health boards at May SPB | One of the challenges highlighted in the Cluster Survey was the ability to employ staff at Cluster level. CICs offer a solution and allow access to a wider range of funding sources |
| 19 | April-Sept | Develop proposals to ensure that there is good and effective stakeholder, public and patient engagement in Clusters and PCPGs | RPBs, PCPGs, HB Exec Teams | To Consider | Three of the seven health boards report this as complete, with four reporting as ongoing / work in progress SPPC Action: Recognised work in progress; review with the four health boards reporting as ongoing / in progress at May SPB | Clusters are the local footprint for health and social care services. Stakeholder, public and patient engagement should be a core aspect of all service development approaches. This is particularly important to ensure that proposed solutions are deliverable within the local context |
| 20 | July-Sept | Professional Collaboratives (where established) begin to respond to published population needs assessments (such as RPNAs published in April 2022) and identify their service gaps and developments in response to Welsh Government planning guidance | Professional Collaboratives | Must Do | Three of the seven health boards report this as complete, with four reporting as ongoing / work in progress SPPC Action: Recognised work in progress; review with the four health boards reporting as ongoing / in progress at May SPB | Professional Collaborative members bring a wealth of knowledge about the experience of their patients and their carers as well as experience of the effectiveness of local health and care systems. Professional teams also gather intelligence about the local population through clinical audit and quality improvement activities. This rich information informs the understanding of population need. RPBs should also ensure that the RPNA and other relevant sources of information are accessible for Clusters to ensure that needs assessments and plans at every level are comprehensive |
| 21 | Aug-Dec | Identified Cluster, with Health Board and RPB partners participates in the PCMW / ACD Peer Review pilot | DPCC, DoP, RPB, Cluster | Work in progress | Completed by all Health Boards Reported as complete by all seven health boards | Plans have been in place for 10 years and should play a central role in informing the Health Board of critical local issues and priorities Plans assist local coordination between teams and services to ensure seamless care and the most efficient use of resources The clarity of existing plans is critical for briefing and engaging the new Professional Collaboratives and Pan Cluster Planning Groups: - To understand where the focus of current effort is placed - To contribute to effective solutions for current challenges |
| 22 | Sept - Nov | Clusters begin to use the Professional Collaboratives’ (where established) responses to update the Cluster Plan to address identified needs assessments and service gaps | Clusters | Work in progress | Two of the seven health boards report this as complete, with five reporting as ongoing / work in progress SPPC Action: Recognised work in progress; review with the five health boards reporting as ongoing / in progress at May SPB | Transparency and governance of the use of public money is essential. Spending plans have been in place for seven years but to inform new discussions there needs to be clarity of resource available to support new initiatives The aim of cluster working is to encourage and support collaboration of services around a local community and to test new solutions. This requires clear pathways to test, evaluate and mainstream where projects are successful, releasing resource for further innovation |
| 23 | Dec 2022 | Pan Cluster Planning Groups use the Cluster responses to produce a prioritised countywide response to the RPNA and a 3 year plan for 2023-26. These plans also identify those services which are most effectively delivered on a Cluster footprint | PCPGs | Work in progress | Three of the seven health boards report this as complete, with four reporting as ongoing / work in progress SPPC Action: Recognised work in progress; review with the four health boards reporting as ongoing / in progress at May SPB | This provides clarity of planning and operational footprints. Leads need to understand the organisational architecture and local decision making systems |
| 24 | Jan 2023 | Health Boards use Pan Cluster Planning Group response to Regional Population Needs Assessments [RPNAs] & 3 year plans to inform their 2023-26 IMTPs | DoPs | Work in progress | Five of the seven health boards report this as complete, with one reporting as ongoing / work in progress and one reporting work has not yet started. SPPC Action: Review predicted completion date with one health board and review planned start date with one health board at May SPB | This ensures clarity of connection from the RPB to the Cluster footprint and is a key requirement to ensure the effectiveness of the partnership agenda between health boards, local authorities and third sector providers |
| 25 | Jan - March | RPBs use Pan Cluster Planning Group responses to the RPNAs and 3 year plans to inform their next Area Plans assessments & plans | RPBs | Work in progress | Two of the seven health boards report this as complete, three reporting as ongoing / work in progress and two reporting work has not yet started. SPPC Action: Review with five ‘in progress’ and two ‘not started’ health boards at May SPB | The aim of the PCPG is to deliver the principles of the Social Services & Well-being Act 2014 (the Act), The Wellbeing of Future Generations Act (2015) and A Healthier Wales The PCPG will: - Lead the development of an integrated plan which addresses the health, care and wellbeing needs of the whole population of [County] - Support the implementation at local level of the joint partnership agenda, including (but not limited to) - Cluster plans - Integrated [County] plan - Priorities determined by the RPB and the [County] Partnership Board (PSB) - Requirements of the individual organisational plans which involve partnership working - Bring together senior leaders from the NHS, Local Authority (to agree which departments) and key partners in the Third Sector The Cluster Survey highlighted the need for greater influence from Clusters into the wider health and social care system PCPGs also highlight opportunities from time limited to funding streams (such as winter pressures etc.) |
| 26 | Jan – March 2023 | 2023/2024+ Cluster Funding investment plans are agreed with stakeholders and endorsed by the PCPG | PCPGs, Cluster / Collaborative Leads | Work in progress | Four of the seven health boards report this as complete, two reporting as ongoing / work in progress and one reporting work has not yet started. SPPC Action: Review with two ‘in progress’ and one ‘not started’ health boards at May SPB | This ensures that Health Boards are supporting and enabling the business of the Board through the agreed local footprints, informed by the knowledge and experience of the workforce Effective governance structures and processes ensure that HBs understand the maturity of local partnership arrangements and that they put in place appropriate organisational development support PCPGs will be highlighting risks and opportunities from primary and community care services so that HB Governance systems are complete- taking a whole system view that reflects patient, public and workforce experience |
| 27 | April 2023 | RPBs publish their 5 year Joint Area Plan which should be informed by pan Cluster responses | RPBs | Work in progress | One of the seven health boards report this as complete, with six reporting as ongoing / work in progress SPPC Action: Recognised work in progress; review with the six health boards reporting as ongoing / in progress at May SPB | Clusters were established to support a collaborative approach between ALL local health and social care services serving a defined population The Cluster Survey highlighted that whilst GP practices were established at the core of this approach, the engagement of other contractor services, nursing, AHP, social services and third sector is variable Professional Collaboratives are being introduced to increase workforce engagement. The GP collaborative supports GP practices to address issues specific to General Practice (including sustainability concerns) and similar arrangements apply for the other contractor professions, nursing and AHP Local authorities will consider how similar arrangements might support social care teams. This allows the Cluster to achieve the original aim of a multi-disciplinary forum for holistic needs assessment, collaborative discussions and innovative projects |
| 28 | 2022/2024 | As PCPG plans identify those services which are best delivered for the Cluster population footprint, Clusters will respond by establishing a range of Cluster delivery vehicles | PCPGs, Clusters and Contractors | Work in progress | One of the seven health boards report this as complete, five health boards reporting as ongoing / work in progress and one health board reporting work has not yet started. SPPC Action: Review with five ‘in progress’ and one ‘not started’ health boards at May SPB | As above |
| 29 | 2022/2024 | Health, Social Care and wider partnership funding opportunities (e.g. Regional Investment Fund RIF) considered to support implementation of Cluster plans | PCPGs, Clusters, HB Execs, DSS | Work in progress | Six of the seven health boards report this as ongoing / work in progress and one health board reporting work has not yet started. SPPC Action: Review with all health boards at May SPB | Ensuring that form follows function – i.e. that systems support and enable the shared purpose PCs and PCPGs will only be successful if they are able to deliver change - they need to be able to respond to local challenges and make the most of local opportunities The decision making process should be transparent, rapid and easy to follow The Cluster Survey highlighted concerns about slow and opaque systems which limit innovation and discourage clinical engagement |
| 30 | April 2023 | ACD Programme transition year ends; ACD programme closes and PCPG / Cluster / Professional Collaborative working mainstreamed across health and social care planning and delivery landscape | All Partners | Must Do | One of the seven health boards report this as complete, five health boards reporting as ongoing / work in progress and one health board reporting work has not yet started. SPPC Action: Review with five ‘in progress’ and one ‘not started’ health boards at May SPB | The ACD programme is necessarily ambitious - system backlog, increasing demand and public frustration require an active response Clinical leads need to focus on the clarity of needs assessment, prioritisation, colleague engagement and delivery of solutions They require managerial and technical expertise to deliver this programme of work |

# Table 2 – SPPC response to the national actions

| Table 2: SPPC response to the national actions in the ACD Readiness Checklist as at 25 April 2023 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| # | Timescale | Action | Lead / Owner | Status | Commentary | Why is this important? |
| A | April | ACD Toolkit and Cluster Planning Support Portal launched | SPPC Team & PC Hub | Must Do | Complete Toolkit and Portal launched. | The Toolkit provides a practical guide for all aspects of the ACD programme – easily accessible in a single portal Step by step guidance for those new to roles and more detailed content to support the business of Cluster working Provides a range of resources to avoid duplication of effort and support consistency |
| B | 2022/2023 | ACD Toolkit and Cluster Planning Support Portal periodically updated | SPPC Team & PC Hub | Must Do | Ongoing Further information updated within the toolkit as the material is developed. Cluster Planning Support Portal views currently being sought to aid refinement of the portal in late summer. Project management toolkit launched to support Clusters in their roles. | The toolkit is updated to reflect real experience, adapting resources where needed and sharing examples of good practice. As the resources support the delivery of the programme it is vital that they cover current issues |
| C | April 2022/2023 | ACD Action Learning Group established – monthly sharing and learning across Wales | SPPC Team | Must Do | Complete Monthly meetings being held to share and learn across Wales. | The peer network is driving forward a challenging and important agenda. The transition year has a focus on implementation and learning from the introduction of new structures that emerged as recommendations from the Cluster Survey. This leadership group is leading the change within health boards and working at the national level to share experience and ideas This work is supported by the SPPC and a range of partners including HEIW to ensure that the enabling national programmes are fully aligned with the needs of the service |
| D | 2022/2023 | Cluster Development Support Officer Network continues to meet quarterly for peer engagement and shared learning across Wales | PC Hub | Must Do | Ongoing March 2023 meeting received ACD update/ and presentation from PHW about the work underway to refresh the 2014 Cluster Profiles across Wales, providing the opportunity to shape the format and content of the profiles. Quarterly meetings scheduled through 2023/24 | Cluster Support Officers work closely with Cluster Leads in the day-to-day implementation of the Cluster agenda. The readiness checklist provides a useful summary and timeline for actions. Each Cluster area is unique and the Network provides the opportunity to share experience, check out concerns and propose ideas. The SPPC works closely with the group and identifies issues that can be actioned on a ‘Once for Wales’ basis |
| E | May-June | PCMW / Cluster transition year Peer Review process published | SPPC Team & PC Hub | Must Do | Complete PCMW/ACD Monitoring and Evaluation Plan and the Cluster Peer Review process published. Peer Review briefing packs to be sent out to health boards early July. All pilot Peer Review meetings held across Wales. Summary report produced for discussion with SPB at the May meeting to inform the next steps of the Peer Review process across Wales. | Peer review allows those who best understand local systems, and the current pressures, to identify barriers and enablers and to share good practise. Peer review has benefits to clusters, regional partnership boards (Health Boards and Local Authorities) (RPBs) and the Strategic Programme for Primary Care (SPPC), highlighting structures and systems that are working effectively and identifying risks that remain unaddressed. Cluster peer review during the transition year is an opportunity to test out a new process and provide intelligence to inform a regular peer review process. |
| F | April-June | The Strategic Programme for Primary Care [SPPC] establishes a Leadership and OD Programme to support the Professional Collaboratives and Cluster Leads. | SPPC Team and HEIW | Must Do | Complete Working with HEIW the scope and content of the programme has been agreed; universal offer for each professional collaborative Gwella Platforms launched September: A bespoke leadership development course and action learning set for the Pan Cluster Planning Groups Cluster Leads has been commissioned; the first cohort of 20 individuals will commence in May 2023 with further cohorts later in the year | Leaders at all levels face the challenge of supporting current approaches and developing new ways of working to meet the needs of the population and improve the experience of the workforce more effectively. The Leadership Programme will offer core skills and more advanced learning opportunities with support for individuals to build their career path. |
| G | April -September | Work with WG, Senior NHS Executives, LA partners as required to revise codes of practice, guidance/authority of the RPBs. The revised RPB governance, accountability, along with improved integrated planning arrangements will make clear reference to the role of PCPGs and Clusters | SPPC Team, NHS Executives, WG Colleagues and LA partners | Must Do | Ongoing Linked to the Welsh Government Rebalancing Care and Support Strengthening Regional Partnership Boards programme of work. Part 9 Guidance has been updated to include PCPG/Cluster working. To go out for formal consultation in Spring 2023. Work completed with NHS Board Secretaries to agree an ACD Supporting Governance (Model paper for health boards to use across Wales) | A shared sense of purpose across the whole health and care system is essential to achieve the aims of A Healthier Wales. A ‘line of sight’ between strategic planning and delivery within real communities ensures that all of our efforts are directed towards those shared aims. |
| H | April -September | ‘Once for Wales’ Contract and Community Interest Company briefing sessions held for Health Boards and RPB partners | SPPC Team; NHSWSSP, PCC | Must Do | Complete CIC chapter published in the ACD Toolkit (chapter 5) – including case study and interviews. Health Board awareness and information workshops held in August, September & October – all sessions well attended. PCC facilitated workshop in Powys Spring 2023 to support CiC thinking planned | New delivery models offer solutions to practical challenges such as the employment of staff at Cluster level. A small number of Community Interest Companies have been established and offer Health Boards the opportunity to commission specific services to meet local needs. This approach also allows a greater degree of autonomy for the local participants which can allow more rapid problem solving and a greater sense of local ownership. |
| I | April -September | Augment the all Wales communications plan and materials for local use | SPPC Team and WG colleagues | Must Do | Ongoing Range of communications tools included in the ACD toolkit including national slide deck (supporting information chapter) | The Transition Year has an extremely busy programme of work which requires an active communications strategy to keep all stakeholders informed and engaged. |
| J | June – March | ACD Regional Hacks commence | SPPC Team | Must Do | Regional hack arranged 23rd November 2022 to focus on national specification for an Inclusion Service Methodology will be used for other topic areas as required across Wales. | Hack Days have a positive track record for rapidly developing digital solutions to practical challenges. This dynamic problem-solving approach could be supported for a wider range of issues if members of the Action Learning Group determine that this will add value. |
| K | April -December | Embed the requirements for Regional Partnership Boards to work with PCPGs (though updated planning and funding guidance) | SPPC Team and WG colleagues | Must Do | Ongoing Linked to G above: Linked to the Welsh Government Rebalancing Care and Support Strengthening Regional Partnership Boards programme of work Part 9 guidance. | A shared sense of purpose across the whole health and care system is essential to achieve the aims of A Healthier Wales. A ‘line of sight’ between strategic planning and delivery within real communities ensures that all of our efforts are directed towards those shared aims. |
| L | June | Cluster Handbooks are refreshed and uploaded onto PCOne | PH Hub | Must Do | Rescheduled – Handbooks to be published in 2023/24. | The handbooks provide practice advice, ideas and tips to help working with clusters. |
| M | July | Cluster / Pan Cluster Planning Group Planning Guidance for 2023/24 published | SPPC Team WG colleagues | Must Do | Complete Guidance published in October 2022 alongside national NHS Planning Framework. Documents uploaded to the Cluster Planning Support Portal : | The links between different levels within the system need to be clear to ensure that each part is contributing to the shared aim of more effectively meeting the needs of communities and making it easier for the workforce to deliver the high standards of care to which they aspire. |
| N | September | Solutions to Information Governance issues published |  | Must Do | Ongoing Insight Paper commissioned by SPCC with YMA; received in Q3. Informed an agreed work programme to be lead by DHCW reporting through to the Data and Digital workstream. Actions to be progressed over 2023/24. | Clarity in the management of Information Governance is an example of a Once for Wales solution that ensures consistency and the best systems to support care. |
| O | Sept – March 2023 | PCMW / Cluster transition year Peer review commences; reflective report and future peer review guidance produced | SPPC Team, Clusters, RPBs | Must Do | Complete Peer review process concluded in March ’23. Summary report and recommendations in development for discussion Q1 2023/24 | The Peer Review cycle in 2022/23 will inform the evaluation of Cluster working and provide recommendations for an established programme of Peer Review from 2023 onwards |
| P | December | Learning from the SPPC commissioned Professional Collaborative Optometry pilot shared across Wales | SPPC Team | Must Do | Ongoing End of year reflections report due Q1 2023/24. Ongoing discussions through the Optometry Contract Reform process. | Professional Collaboratives provide an opportunity for strengthened peer support, local collaboration and increased influence for professional groups. The pilot project allows us to test this approach, to learn from that experience and adapt as needed. |
| Q | December | Strategic Programme for Primary Care Fund 2022 ACD investment interim report produced | SPPC Team | Must Do | Complete Mid year update summary report produced and shared via SPPC governance route to DPCC and presented to NPCB in November 2022. End of Year 1 progress report under development. | The Interim Report will summarise how investment has been used, highlight what has worked well and share that knowledge across the system to inform local approaches. |