| Why is the Project needed? During 2022/23, the Mental Health & Wellbeing (MHWB) project conducted a national review that was commissioned to provide a greater understanding on key themes for providing mental health support in Primary Care, demand and activity, variation in National Health Service Primary Care Mental Health Service provision and third-sector mental health support at Primary Care level. The national review found that although there are positive steps being taken in most areas of Wales to meet rising demand and to deliver services that meet individuals mental and emotional health needs, there are still many areas that require further work and focus. Therefore, the workplan for 2023/24 includes a number of areas that will, in turn, help to understand the impact & influence of the first stage of the work. Including; - Gathering examples of where the 2022 report has informed / influenced ongoing and new pieces of work, strategy, or service development (including the renewed Together for Mental Health Strategy) - Development of consistent terminology & definitions - Provide understanding and clarity on the interface and overlap between Primary Care Mental Health (PCMH) Services, Social Prescribing, Local PCMH Support Services & Secondary Care Mental Health Services - Provide a framework for consistent commissioning of third sector services & assurance that local third sector provision sufficiently addresses local demand - Exploring the options and requirements of a ‘national minimum offer’ | Key Deliverables Q1 - Formally issue report to all cluster leads advising of intention to scope impact of report - Develop a template for sharing with stakeholders to gather intelligence re: how the 2022 report has informed / influenced ongoing and new pieces of work, strategy, or service development (including the renewed Together for Mental Health Strategy) - Draft and issue specification for third-party literature review of terminology and definitions - Commence development of a framework for consistent commissioning of third sector services & assurance that local third sector provision sufficiently addresses local demand (NCCU leading, work commenced 1 April ’23) - Establish project group of required stakeholders and scope / confirm regular meetings throughout 2023/24 Q2 - Share template with stakeholders for intelligence gathering - Review findings from intelligence gathering exercise and use findings to inform next steps - Review the social prescribing interfaces paper and provide recommendations for next steps / requirements re: the interface and overlap between Primary Care Mental Health (PCMH) Services, Social Prescribing, Local PCMH Support Services & Secondary Care Mental Health Services and provide some preliminary recommendations - Project group meetings formally commence - Scoping / requirements for national minimum offer framework Q3 - Review outcome from third-party literature review - Finalise, translate, and publish the Glossary of Terms - Commence development of the national minimum offer framework Q4 - Finalise, translate, and publish the framework for consistent commissioning of third sector services - Finalise, translate and publish the national minimum offer framework |
| --- | --- |
| What is the scope of the project? Phase 2 of the project will develop on the work conducted during 2022/23, with a focus on - Engagement with stakeholders to gather examples & understand how the 2022 report has informed and influenced ongoing and new pieces of work, strategy, or service development (including the renewed Together for Mental Health Strategy) - Commission a review of terminology & definitions to produce a consistent Glossary of Terms to enable consistency across Primary Care and Mental Health strategies and settings - Provide understanding and clarity on the interface and overlap between Primary Care Mental Health (PCMH) Services, Social Prescribing, Local PCMH Support Services & Secondary Care Mental Health Services - Provide a framework for consistent commissioning of third sector services & assurance that local third sector provision sufficiently addresses local demand - Exploring and propose a suite of options to provide a ‘national minimum offer’ |  |

| Interdependencies to note: |  |
| --- | --- |
| - Social prescribing Wales | - Six Goals for Urgent and Emergency Care – Goal 1 |

| Outputs – actions or items contributing to achieving an outcome | Outcomes – what we want or need to achieve/changes we expect to result from this work | Link to Six Goals | link to PCMW |
| --- | --- | --- | --- |
| - MHWB Glossary of Terms | Standard Glossary of Terms nationally agreed and adopted across Wales | Goal 1 | Outcomes 1, 3, 4 |
| - Framework for consistent commissioning | Nationally agreed framework developed and adopted across Wales |  |  |
| - Framework for a ‘national minimum offer’ | Adoption and implementation of a national minimum offer to ensure and demonstrate equity of services |  |  |

Mental Health & Wellbeing phase 2 Outcomes

| Six Goals for Urgent and Emergency Care |  |
| --- | --- |
| Goal 1. Supporting people at more risk of needing urgent or emergency care |  |
| Goal 2. People are told where they can get the help they need |  |
| Goal 3. Other choices than hospital |  |
| Goal 4. Reacting quickly in a health emergency |  |
| Goal 5. People get the best care in hospital and when they leave |  |
| Goal 6. Home when possible |  |

Primary Care Model for Wales Outcomes - how care will be delivered locally, now & in the future, as part of a whole system approach to deliver A Healthier Wales

| Outcome 1 An informed public | Outcome 8 Directly accessed services |
| --- | --- |
| Outcome 2 Empowered communities | Outcome 9 Integrated care for people with multiple care needs |
| Outcome 3 Support for well-being, prevention & self-care | Outcome 10 Cluster estates & facilities support multi-professional working |
| Outcome 4 Local services | Outcome 11 Cluster IT systems enable cluster communications & data sharing |
| Outcome 5 Seamless working | Outcome 12 Ease of access to community diagnostics supporting high-quality care |
| Outcome 6 Safe & effective call handling, signposting & triage | Outcome 13 Finance systems designed to drive whole-system transformative change |
| Outcome 7 Quality out-of-hours care |  |