| Why is the Project needed? Nationally, Welsh Government has recognised the potential of social prescribing with it featuring across a number of policies and strategies including Together for Mental Health delivery plan (2019-2022) and Connected Communities: a strategy for tackling loneliness and social isolation and building stronger connections, in addition to making a Programme for Government 2021-2026 commitment to introduce an all-Wales framework to further support the roll-out of social prescribing. One of the key priorities identified for 2023/24 will be to support the ongoing development and implementation of the national framework for social prescribing, providing leadership to the system and targeted support to primary and community care to appreciate it’s potential. There is an identified requirement, within the Social Prescribing Interfaces report (PHW, 2022) to: - recognise and address the interface between social, physical and mental health and wellbeing in all polices - support the interaction and synergy between all components in the social prescribing interface model, by making equitable population health and wellbeing central to the planning of services - embed a person-centred approach to accessing services, activities and assets to support people to better manage their health and wellbeing - support those referring to social prescribing with understanding the role and purpose of services, activities and assets to support different needs - achieve the long-term outcomes of social prescribing, there is a need to increase the scale and sustainability of services, activities and assets that social prescribing relies on. The vision for the programme is to support the development and implementation of social prescribing in Wales to improve individual physical, mental and social wellbeing and community wellbeing, as well as to have a system impact on the wider determinants of health. | Key Deliverables Q1 - Collate case studies to demonstrate how health & wellbeing needs can be addressed through social prescribing - Support delivery of competence framework for social prescribing practitioners in Wales - Support delivery of a coordinated communication strategy to promote key SP resources and publications including national framework, glossary of terms, competence framework, social prescribing interfaces paper - Support USW to recruit Research Assistant funded via PCD/PHW grant and agree programme of work to include Scope approach and content for resource to demonstrate evidence for meeting health & wellbeing needs through social prescribing Q2 - Scope approaches to support the cost-of-living crisis and income maximisation through social prescribing - Scope actions required to support ongoing development and implementation of the national framework for social prescribing - Joint review of logic model and outcomes framework for social prescribing - Conclude recruitment with USW of Research Assistant Q3 - Work in partnership with WG / stakeholder partners to organise and host a Welsh Social Prescribing conference - Publish social prescribing case studies - Publish Glossary of Terms for Social Prescribing - Support development of outcomes framework for social prescribing (Connected Communities deliverable) incorporating PC Hub developed logic model - Agree and plan approach(es) to supporting the cost-of-living crisis and income maximisation through social prescribing Q4 - Develop resource to demonstrate evidence for meeting health & wellbeing needs through social prescribing |
| --- | --- |
| What is the scope of the project? This project is intended to: - contribute to the ongoing development and implementation of the national framework - coordinate to SP deliverables from the Connected Communities Strategy as appropriate to the direction of the national framework - collaborate with the breadth of stakeholders involved in social prescribing, reflecting the cross-sectoral nature of the approach - engage with primary and community care stakeholders to support their understanding of how social prescribing can support a range of health and wellbeing needs - provide leadership and represent public health and primary care perspectives via the Social Prescribing Coordinating Group - develop products to support the further advancement of social prescribing as a key mechanism to progressing the wellbeing agenda in Wales. |  |
| Interdependencies to note – |  |
| - WG National Framework for Social Prescribing - Successful recruitment of Research Assistant by USW |  |

| Outputs – actions or items contributing to achieving an outcome | Outcomes – what we want or need to achieve/changes we expect to result from this work | Link to Six Goals | link to PCMW |
| --- | --- | --- | --- |
| - Glossary of terms for social prescribing | Greater standardisation of social prescribing language in Wales, supporting clarity and facilitating communication |  | Outcomes 2,3,4,5, 8, 9 |
| - Competence framework for social prescribing practitioners in Wales | Increased understanding and standardisation of the role and requirements of social prescribing practitioners |  |  |
| - Social prescribing case studies | Greater understanding the role and purpose of services, activities and assets to support different needs |  |  |
| - ‘Meeting health & wellbeing needs through social prescribing’ outputs |  |  |  |
| - International Social Prescribing Evaluation Conference | Develop networks, shared learning, show case social prescribing in Wales |  |  |
| - Revised logic model and outcomes framework for social prescribing | Unify two outputs, support understanding of anticipated outcomes of social prescribing, support monitoring and evaluation of social prescribing in Wales |  |  |

Social Prescribing Outcomes

| Six Goals for Urgent and Emergency Care |  |
| --- | --- |
| Goal 1. Supporting people at more risk of needing urgent or emergency care |  |
| Goal 2. People are told where they can get the help they need |  |
| Goal 3. Other choices than hospital |  |
| Goal 4. Reacting quickly in a health emergency |  |
| Goal 5. People get the best care in hospital and when they leave |  |
| Goal 6. Home when possible |  |

Primary Care Model for Wales Outcomes - how care will be delivered locally, now & in the future, as part of a whole system approach to deliver A Healthier Wales

| Outcome 1 An informed public | Outcome 8 Directly accessed services |
| --- | --- |
| Outcome 2 Empowered communities | Outcome 9 Integrated care for people with multiple care needs |
| Outcome 3 Support for well-being, prevention & self-care | Outcome 10 Cluster estates & facilities support multi-professional working |
| Outcome 4 Local services | Outcome 11 Cluster IT systems enable cluster communications & data sharing |
| Outcome 5 Seamless working | Outcome 12 Ease of access to community diagnostics supporting high-quality care |
| Outcome 6 Safe & effective call handling, signposting & triage | Outcome 13 Finance systems designed to drive whole-system transformative change |
| Outcome 7 Quality out-of-hours care |  |