| Why is the Project needed? The demand for more informed healthcare metrics in primary care continues to grow. Equally important is an effective and accessible platform for communicating that data and key messages. There is an immediate need for a product that delivers high level Primary care headline information. The question is whether it is possible to provide primary care information, that has face validity, is easily extractable, and currently available, presented in an all Wales format for use in standardised messaging, for example, with the Health Minister, IQPDs and other key stakeholders. This project would review what data information and platforms are already available, as well as potential tools. The project will compile a meaningful minimum data set and agree a standard presentational style and platform. Such as: - A profile of primary care (eg number of practices, premises, services they deliver) - Primary care activity and performance - Build in community services data and Healthy Days at Home Wales measure The project will identify the potential outputs that could evolve from a larger project around primary care information display. | Key Deliverables Stage one: Scoping and Discovery - Mapping exercise to identify metrics already out there - Identify possible platforms - Ensure close alignment with interdependent information systems/projects - Consider information / data governance requirements Stage two: Engagement with primary care stakeholders - What initial information would stakeholders want on the platform - Defining the ‘so what’, how the information will be used Stage three: Develop a primary care metrics minimum data set - Compile a specification listing the agreed minimum data sets - Submit to Health Boards for confirmation - Agree platform/format of presentation - Submit final specification to platform for delivery Stage four: Launch primary care metrics minimum data set - Develop a detailed launch comms plan and timeline Stage five: Evaluation - Monitor platform for hits and reach - Issue feedback form for possible iterations to the data sets and presentation and analysis capabilities - Make recommendations for the larger pc information display project eg. Gap analysis exercise regarding existing metrics |
| --- | --- |
| What is the scope of the project? - The work will be based upon a ‘good enough’ approach and aim for early realisation of a viable product for continual refinement going forward. - Working with data sets already available in the majority of Health Boards. - Working with platforms that are currently available (ie PowerPoint slide, Power BI dashboard etc.) What is Not in the scope of the project? - Creating wholly new national datasets and identifying data sources. |  |
| Interdependencies to note |  |
| - Health Board PC management teams’ business cycles (HoPC) - DHCW (NDR, NHS App, PCIP) - Information Standards Board (WISB) | - SPPC (Escalation Framework, Healthy Days at Home Wales, Community Infrastructure, PC Information Display, PC Measures 2018) - Welsh Government NHS Planning Framework Minimum Data Set (MDS) |

| Outputs – actions or items contributing to achieving an outcome | Outcomes – what we want or need to achieve/changes we expect to result from this work | Link to Six Goals | link to PCMW |
| --- | --- | --- | --- |
| - Scoping Report | Identify MDS and platforms available | Goal 4 | Outcomes 3,4,5,7, 10,11, 12,13 |
| - Stakeholder survey | Ensure engagement with stakeholders to reach MDS identification |  |  |
| - Minimum data set specification | To outline exactly what is required for the new presentation (MVP) |  |  |
| - Platform and product | Platform and product |  |  |
| - Launch and comms plan | To ensure reach and communicate benefits of new MDS display |  |  |
| - Post delivery feedback survey | Evaluation, next steps and inform larger pc information display project |  |  |

| Six Goals for Urgent and Emergency Care |  |  |  |  |
| --- | --- | --- | --- | --- |
| Goal 1 | Supporting people at more risk of needing urgent or emergency care |  |  |  |
| Goal 2 | People are told where they can get the help they need |  |  |  |
| Goal 3 | Other choices than hospital |  |  |  |
| Goal 4 | Reacting quickly in a health emergency |  |  |  |
| Goal 5 | People get the best care in hospital and when they leave |  |  |  |
| Goal 6 | Home when possible |  |  |  |

| Primary Care Model for Wales Outcomes - how care will be delivered locally, now & in the future, as part of a whole system approach to deliver A Healthier Wales |  |  |  |
| --- | --- | --- | --- |
| Outcome 1 | An informed public | Outcome 8 | Directly accessed services |
| Outcome 2 | Empowered communities | Outcome 9 | Integrated care for people with multiple care needs |
| Outcome 3 | Support for well-being, prevention & self-care | Outcome 10 | Cluster estates & facilities support multi-professional working |
| Outcome 4 | Local services | Outcome 11 | Cluster IT systems enable cluster communications & data sharing |
| Outcome 5 | Seamless working | Outcome 12 | Ease of access to community diagnostics supporting high-quality care |
| Outcome 6 | Safe & effective call handling, signposting & triage | Outcome 13 | Finance systems designed to drive whole-system transformative change |
| Outcome 7 | Quality out-of-hours care |  |  |